## Main
DOCMEE
Command Center — planning & build tracker
AI chatbot platform for clinics · single source of truth · all data live
KEY METRICS
Phases sealed | 12 / 12
Decisions locked | 64
Decisions parked (revisit) | 0
Open risks (Med-High +) | 1
Security items open | 5
Requirements partial/gap | 1
Est. dev hours (plan) | 650
Actual hours logged | 5
AI uses logged | 24
Grand cost (to date) | 112
TABS · all hidden — right-click the Main tab ► Unhide to open any sheet
▸ Overview |  | ▸ Risk Register
▸ Action Tracker |  | ▸ Phase Gates
▸ Decisions Index |  | ▸ Progress (Gantts)
▸ Platform Requirements |  | ▸ Security Audit
▸ Cost Tracker |  | ▸ Gaps
▸ Pros |  | ▸ Cons
▸ Future Improvements |  | ▸ Update Log
▸ Build Backlog
To open a sheet: right-click the 'Main' tab at the bottom ► Unhide ► choose the sheet. (Excel desktop / Google Sheets: View ► Hidden sheets.)
OPEN DECISIONS & GAPS
• PLANNING COMPLETE — 12 phases sealed + cross-cutting retention/observability/compliance (GDPR-baseline) locked. Next: build.
• Pre-launch actions: testing/QA execution (X19) · Guatemalan data-protection counsel review (X20) · backups (X12) · deflection sign-off (X14)
• Deferred by design (FI1–FI8): live calendar sync · self-host LLM · license · native app · billing · smarter merge · bot reschedule/cancel · broadcast
• Build-time gates (Phase Gates tab) + per-clinic onboarding (X1–X18) handled during implementation
CONFIDENCE (Phase 0 → 3D) · flag line = below 8.0
Total decisions scored | 64
Average confidence | 8.48
Lowest score | 7.5
Decisions ≥ 9.0 | 6
Decisions = 8.5 | 50
Decisions = 8.0 (lowest locked tier) | 7
Decisions below 8.0 (FLAGGED) | 1
🚩 Below 8.0: 2B / cross-channel identity merge = 7.5 — deliberate manual-merge (avoids PHI-mixing); recorded as a Con + FI6. Knowingly flagged, not an oversight.
At 8.0 (watch list): 1B Data capture · 2A Notifications · 2B Unified inbox · 3A Doctor routing · 3B Flow builder · 3B Secretary copilot · 3C Sheets/CRM export

## Overview (hidden)
Docmee — Project Trackers
Consolidated living workbook · risks, external actions, phase gates, decisions, update log
Last updated: 13 June 2026
Phase status (all 12 phases)
Phase | Status
0 — Foundation | Sealed
1A — Core Inbox + Bot | Sealed
1B — Human Inbox + Patient Data | Sealed
1C — Scheduling | Sealed
2A — Multi-User Operations | Sealed
2B — Channels | Sealed
2C — Automation & Templates | Sealed
2D — Analytics & Search | Sealed
3A — Multi-Doctor | Sealed
3B — Advanced Intake | Sealed
3C — Integrations & OCR | Sealed
3D — Mobile / PWA / Push | Sealed
Summary (live counts — recomputed each run)
Metric | Count
Risks — Med-High priority | 1
Risks — Medium priority | 4
Risks — Low priority | 8
Actions — Not started | 15
Actions — In progress | 2
Actions — Blocked/waiting | 1
Actions — Closed | 1
Actions — Parked | 1
Phases — Sealed | 12
Security — Open items | 5
Requirements — Partial/Gap (to address) | 1
Legend
Term | Meaning
Owner | Clinic = end-user clinic · Docmee = Docmee team
Path | Dev path = blocks the build · Off dev path = does not block the build
Priority | High / Med-High / Medium / Low (likelihood × severity)
Tabs | Risks · Actions · Gates · Decisions · Gaps · Pros · Cons · Progress · Security Audit · Future Improvements

## Risk Register (hidden)
ID | Risk | Owner | Affects | Likelihood | Severity | Priority | Path | Disposition / Status
R1 | Meta asset transfer / WhatsApp setup (already verified, same entity) | Clinic | Per-clinic go-live | Low | Med | Low | Off dev path | Largely retired — routine; clinic-owned
R2 | Message-template approval (2C, outside 24h window) | Clinic | Per-clinic 2C automation | Med | Med | Low | Off dev path | Clinic responsibility; Docmee may supply content
R3 | Legal docs (privacy policy, terms, Spanish) | Clinic | Per-clinic launch | Med | Med | Medium | Off dev path | Open — clinic-owned; Docmee supplies template (X11)
R4 | App-layer encryption breaks SQL filtering | Docmee | Patient lookup, matching, dedupe | Low | Med | Low | Dev path | De-risked & locked: separate stable HMAC key; DAL lookups; ciphertext never in WHERE
R5 | RLS cross-tenant carve-out done wrong → isolation leak | Docmee | Workers, metrics, DLQ, IA Studio | Low | High | Low | Dev path | De-risked & locked: named admin role + withAdminContext() + allowlist + audit
R6 | Single-clinic-per-user may not fit a clinic-group customer | Docmee | Auth/JWT/RLS if revisited | Low | Med-High | Low | Dev path | Accepted — one-to-one locked; bounded future migration
R7 | Unofficial WhatsApp gateway (Evolution) for interim/live traffic | Docmee tech/ops | Channel continuity; PHI custody | Med | High | Medium | Off dev path | Accepted — bounded by interim use + supervision; prompt X10 cutover
R8 | Single-VPS = single point of failure | Docmee tech/ops | Availability once real clinics depend | Med | High (Low w/ backups) | Medium | Off dev path | Redundancy deferred (X13); backups REQUIRED before real patients (X12)
R9 | Document ingestion expands Phase 1A scope | Docmee | 1A timeline; embedding spend | Med-High | Med | Med-High | Dev path | Open — mitigated (text-layer, off-the-shelf libs, OCR→3C); fallback end-1A/early-1B
R10 | Bot mis-handles a distress message (booking-only clinics) | Docmee + Clinic | Reputation; liability | Low | Med | Medium | Safety | Reduced — minimal deflection guardrail; clinic sign-off (X14)
R11 | Cross-channel / duplicate patient records | Docmee | CRM data quality; history continuity | Med | Low-Med | Low | Dev path | Mitigated — manual staff-merge in 2B (audited, confirmation); smarter auto/suggested/reversible merge → FI6
R12 | No message-content search in 1B (message bodies encrypted) | Docmee | Inbox search UX; clinic expectation | Low | Low | Low | Dev path | Resolved — 2D adds per-clinic full-text message search (tsvector+GIN, RLS, audited); 1B shipped structured filters + identity (HMAC) search
R13 | Bot patient-data mis-capture (extraction accuracy) | Docmee | CRM data quality | Med | Low | Low | Dev path | Accepted/mitigated — confidence-gating (verified vs suggested), secretary-edits-win, per-field source, no deletes, full audit; tune on real traffic

## Action Tracker (hidden)
ID | Item | Owner | Blocks / Needed by | Lead time | Status
X1 | Transfer Meta (WhatsApp/WABA) asset into Docmee/clinic app | Clinic | Per-clinic go-live (off dev path) | ~Days | In progress
X2 | Interim WhatsApp connectivity via self-hosted Evolution API (supervised, interim) | Docmee tech | Phase 0 Track A + early onboarding | Days | In progress
X3 | Draft + publish privacy policy & terms (Spanish) | Clinic | Per-clinic launch (off dev path) | 1–2 weeks | Not started
X4 | Draft + submit WhatsApp message templates | Clinic (Docmee content) | Per-clinic 2C (off dev path) | 1–3 wks/batch | Not started
X5 | Provision third-party API creds — Docmee platform keys (Model A); transcription provider-abstracted | Docmee | 1A end-to-end (not start) | Hours–days | Not started
X6 | Stand up Supabase + Redis + VPS + DNS (+ Storage) | Docmee | Phase 0 deploy target | Hours–days | Not started
X7 | Per-clinic WhatsApp display-name approval + number (Cloud API) | Clinic | Per-clinic go-live official API (off dev path) | Days | Blocked/waiting
X8 | Encryption key source | Docmee | Phase 0 | — | Closed — Supabase Vault + envelope + key_version; host-store fallback
X9 | Stand up & maintain self-hosted Evolution API in Docmee infra | Docmee tech | X2 interim + 1A end-to-end testing | Days | Not started
X10 | Per-clinic cutover: Evolution → Meta Cloud API | Docmee tech | End-state channel per clinic | Per clinic | Not started
X11 | Clinic onboarding-support checklist/guide | Docmee | Smooth onboarding; protects launch | Days | Not started
X12 | VPS backup + recovery plan (mitigates R8) | Docmee tech | Before real patient traffic | Days | Not started
X13 | Redundancy / HA build-out (Redis external → multi-node → LB) | Docmee tech | Trigger: first real patients / SLA | 1–4 weeks | Parked
X14 | Deflection-message sign-off + local emergency number (mitigates R10) | Clinic + Docmee | Before real patient traffic | Mins–hours | Not started
X15 | Per-clinic Google Calendar connection (OAuth consent + select calendar) + availability schedule config (hours, slot length, buffers) | Clinic (Docmee guidance) | Per-clinic booking (1C) | Mins–hours | Not started
X16 | Per-clinic Messenger + Instagram channel connection (connect Facebook Page / IG account via Meta) | Clinic (Docmee guidance) | Per-clinic multi-channel (2B) | Mins–hours | Not started
X17 | Per-doctor Google Calendar connection (each doctor connects their own calendar; multi-doctor clinics) | Clinic + doctor (Docmee guidance) | Per-doctor scheduling (3A) | Mins–hours | Not started
X18 | Per-clinic Google Sheets / CRM connection (OAuth/credentials + field mapping) for lead/patient export | Clinic (Docmee guidance) | Per-clinic integrations (3C) | Mins–hours | Not started
X19 | Testing/QA execution — layered suite: unit · integration · provider-abstraction contract · E2E · RLS/tenant-isolation · six-gate/idempotency · LLM safety-eval harness; CI per PR + seeded staging | Docmee tech | Post-deployment QA hardening (per scope: tracked here, non-blocking to core dev) | Ongoing | Not started
X20 | Guatemalan data-protection counsel review — consent, retention, health-data + export obligations; confirm GDPR-baseline design (complements X3 privacy policy) | Docmee + local counsel | Before real patient traffic | Days | Not started

## Phase Gates (hidden)
Phase | # | Gate criterion (pass/fail) | Result | Notes
0 | 1 | Inbound message stored, normalized, scoped to correct clinic_id | Pending
0 | 2 | Cross-tenant read denied at the DB (RLS proven) | Pending
0 | 3 | Worker assumes clinic context (SET LOCAL); admin role only cross-tenant path | Pending
0 | 4 | Redelivered wamid → exactly one row (idempotency) | Pending
0 | 5 | Outbound delivers; send to opted-out patient blocked at chokepoint | Pending
0 | 6 | Unknown phone_number_id logged + metric + dropped (no crash/row) | Pending
0 | 7 | Ciphertext at rest; HMAC lookup resolves; key_version recorded | Pending
0 | 8 | Clinic JWT scoped; platform users only via logged impersonation | Pending
0 | 9 | Migrations apply clean forward from empty DB; /health/ready green | Pending
1A | 1 | KB entries + text-layer doc → chunks embedded → review→live; retrieval ≥0.70; rules injected | Pending
1A | 2 | Intent + routing; taken-over conv never auto-replies; distress → deflection; no reply without decision token | Pending
1A | 3 | KB-covered question → grounded answer; no-KB → acknowledge + handoff (no hallucination) | Pending
1A | 4 | Free-form inside 24h; out-of-window reply held → resend once → escalate | Pending
1A | 5 | Inbox real-time; manual reply chokepoint-checked; takeover/resolve; inactivity revert silent | Pending
1A | 6 | Spanish voice note transcribes → text pipeline; fail → retype; repeat → handoff | Pending
1A | 7 | First bot reply of a new conversation includes one-time disclosure | Pending
1A | 8 | Provider 429/5xx → bounded retry → handoff + holding message (no crash/hang) | Pending
1A | 9 | Inbound >30 days → new conversation; resolved + inbound <7 days → reopen in bot mode | Pending
1A | 10 | Failed embedding job → retry → mark chunk failed + flag doc incomplete; others unaffected | Pending
1B | 1 | Patient auto-created on first contact; clinic-scoped one-per-identity | Pending | Q1 (in progress)
1B | 2 | Patient progressively enriched; valid with identity only | Pending | Q1
1B | 3 | patient_id backfilled onto 1A conversations; inbound resolves-or-creates | Pending | Q1
1B | 4 | Functional patient profile: history, tags, statuses, notes, search/filter | Pending | Q2
1B | 5 | Shared queue + claim; reply/takeover auto-assigns; reassign allowed | Pending | Q2
1B | 6 | Free-form multi-tags + patient status; conversation state = mode (no duplicate) | Pending | Q2
1B | 7 | Patient-level internal notes (authored + timestamped, staff-only) | Pending | Q2
1B | 8 | Inbox filters (mode/assignment/tags/status/date) + patient-identity search | Pending | Q2
1B | 9 | Bot captures name/reason via tool-calling → validated DAL writes (field-level, logged, no deletes) | Pending | Q3
1B | 10 | Ambiguous capture confirmed or written as suggested (not committed); never fabricates | Pending | Q3
1B | 11 | Per-field source (bot/staff); secretary-set fields locked from bot overwrite | Pending | Q3
1B | 12 | Handoff/distress → urgent notification (panel + email); new lead → panel; visible until acknowledged | Pending | Q4
1B | 13 | Clinic-level email config: recipients + per-event toggles; dispatcher honors config | Pending | Q4
1B | 14 | patient_id backfill links existing conversations; resolve-or-create on inbound | Pending | Sweep
1B | 15 | Patient profile shows conversation-list + data/tags/notes (no merged message-stream) | Pending | Sweep
1B | 16 | RBAC enforced at API/DAL across inbox/profile/notes (Assistant: no reply, no notes) | Pending | Sweep
1C | 1 | Booking creates a linked Google Calendar event (datetime) + appointments row (the rest) | Pending | Q1
1C | 2 | Availability = clinic schedule ∩ Google free/busy; no slot offered that conflicts with calendar busy | Pending | Q1
1C | 3 | One calendar per clinic; per-doctor calendars deferred to 3A | Pending | Q1
1C | 4 | 8-step intake persisted in patient_intake; resumes from saved step after interruption/takeover | Pending | Q2
1C | 5 | Mid-intake digression: bot answers from KB then returns to the intake step | Pending | Q2
1C | 6 | Availability re-validated at write; if slot taken → re-offer fresh slots | Pending | Q2
1C | 7 | Bot completes booking; no-slots/stuck/explicit-person → handoff with partial intake; reschedule/cancel → secretary | Pending | Q2
1C | 8 | Appointment states + logged transitions (appointment_status_log) | Pending | Q3
1C | 9 | Auto-completion job sets completed (now>end+30m) + fires a 2C-bound hook; no-show set manually | Pending | Q3
1C | 10 | Appointments surfaced in patient profile + inbox status; manual changes RBAC-gated + logged | Pending | Q3
1C | 11 | Cancellation cascade: cancel Google event + clear pending; mechanism ready for 2C automation-kill | Pending | Q3
1C | 12 | Calendar outage/disconnect → booking fails safe to handoff + clinic 'Calendar disconnected' alert | Pending | Sweep
1C | 13 | Double-write: event first then row; row-fail compensates (deletes event); reconciliation backstop | Pending | Sweep
1C | 14 | Confirmation reads back absolute clinic-local datetime; UTC stored; DST-correct; horizon + no-past guard | Pending | Sweep
2A | 1 | Clinic selects routing strategy; shared-queue default unchanged from 1B | Pending | Q1
2A | 2 | Round-robin / load-based assign only to available staff; none available → shared queue + notify | Pending | Q1
2A | 3 | Routing never overrides explicit assignment; reassign allowed; RBAC-gated targets | Pending | Q1
2A | 4 | P1–P4 priorities drive differentiated channels (panel/email/push) + escalation behavior | Pending | Q2
2A | 5 | Unacknowledged P1/P2 escalates assignee→all staff→admin→IA Studio; ack stops the ladder | Pending | Q2
2A | 6 | Dedup: repeated events on one conversation collapse into a single active notification | Pending | Q2
2A | 7 | Per-user prefs + quiet hours; P1/safety breaks through quiet hours | Pending | Q2
2A | 8 | Basic web push delivered (service worker + VAPID); native push deferred to 3D | Pending | Q2
2A | 9 | Quick replies insert with context-resolved variables; sent via chokepoint; never auto-sent | Pending | Q3
2A | 10 | IA Studio: clinic/plan/provider config; impersonation stamped + audited; panel RBAC enforced at API/DAL | Pending | Q4
2A | 11 | Manual invoice created/tracked; conversation-limit soft-cap warns + flags overage without cutting off care | Pending | Q5
2B | 1 | Messenger + Instagram inbound normalized to common message shape; outbound via chokepoint | Pending | Q1
2B | 2 | Per-clinic channel connect (FB Page / IG); channel identity encrypted + HMAC | Pending | Q1
2B | 3 | Pipeline (gates/bot) runs channel-agnostic across all channels | Pending | Q1
2B | 4 | Unified inbox shows all channels with channel badge; CRM channel-agnostic | Pending | Q3
2B | 5 | Per-channel messaging-window rules enforced at outbound (WhatsApp/Messenger/IG) | Pending | Q3
2B | 6 | Manual cross-channel patient merge by secretary (audited, confirmation); no auto-merge | Pending | Q2
2B | 7 | Per-channel media/attachment types normalized; unsupported → notice/handoff | Pending | Sweep
2B | 8 | Channel token/connection failure → channel disconnected + clinic alert; that channel's inbound paused | Pending | Sweep
2C | 1 | Templates tracked draft→submitted→approved/rejected (Meta-synced); only approved templates send out-of-window | Pending | Q1
2C | 2 | Every proactive message passes all six gates at the chokepoint; fail any → not sent + logged | Pending | Q2
2C | 3 | Reminder/confirmation jobs scheduled on booking; confirm-reply → confirmed; cancel/reschedule moves/kills jobs | Pending | Q3
2C | 4 | Auto-completion hook fires post-visit follow-up; no-show recovery; all template-gated + per-clinic configurable | Pending | Q4
2D | 1 | Metrics + QoS rollup jobs populate per-clinic aggregate tables; dashboards in IA Studio + clinic panel | Pending | Q1
2D | 2 | Error review queue surfaces categorized bot/agent/API failures; unanswered → KB suggestion | Pending | Q2
2D | 3 | Per-clinic full-text message search (tsvector+GIN, RLS, audited); resolves R12 | Pending | Q3
3A | 1 | Doctor entity active: per-doctor calendar/services/hours/FAQs; doctor=bookable profile ± user account; N=1 backward compatible | Pending | Q1
3A | 2 | Booking intake adds doctor selection when >1 doctor (explicit/specialty/any-available); single-doctor auto-skips | Pending | Q2
3A | 3 | Doctor-aware KB retrieval (clinic-shared + selected-doctor chunks); no cross-doctor leakage | Pending | Q3
3A | 4 | Conversations/appointments associate to a doctor; inbox filter + per-doctor routing/visibility (reuses 2A) | Pending | Q4
3B | 1 | Declarative custom flows run by a deterministic engine; tool steps allowlisted; guardrails enforced; versioned + starter library | Pending | Q1
3B | 2 | Structured conditional rules; safety-critical rules enforced deterministically at gates; tone = rule setting (PR26/PR27) | Pending | Q2
3B | 3 | Secretary copilot (draft/summarize/suggest) human-in-the-loop; never auto-sends; KB-grounded; no cross-clinic PHI | Pending | Q3
3C | 1 | Ingestion handles scanned docs via OCR + docx/structured parsers; low-confidence flagged for review; same KB path | Pending | Q1
3C | 2 | Per-clinic Sheets/CRM export (append + webhook); encrypted creds; clinic-authorized fields only; egress audited | Pending | Q2
3C | 3 | Automated periodic reports (PDF/email/Sheet) from 2D analytics; per-clinic cadence; clinic-scoped | Pending | Q3
3D | 1 | Panel installable as a PWA (manifest + service worker); responsive; native app stays FI4 | Pending | Q1
3D | 2 | Web Push (VAPID) delivers P1–P4 alerts to staff devices; per-user subs; preference + quiet-hours respected; email fallback | Pending | Q2
3D | 3 | PWA reaches parity on secretary daily-driver ops (inbox, bot control, appointments, alerts, notes) | Pending | Q3

## Decisions Index (hidden)
Phase | Area | Locked decision (summary) | Confidence | Score /10 | Flagged | Reason if < 8 | Record
0 | Worker RLS | SET LOCAL app.clinic_id per job; audited admin role for cross-tenant | High | 8.5 |  |  | phase-0
0 | Encryption | App-layer envelope; key in Supabase Vault; key_version; separate stable HMAC key | High | 8.5 |  |  | phase-0
0 | Identities | platform_users vs clinic_users disjoint; impersonation only | High | 9 |  |  | phase-0
0 | Tenancy | User↔clinic one-to-one; doctor seam dormant → 3A | High | 8.5 |  |  | phase-0
0 | Opt-out | opted_out flag, all-stop, outbound chokepoint, bot-irreversible | Mkt-std | 9 |  |  | phase-0
0 | Loop | Pipes only; no auto patient replies (first reply = 1A) | High | 9 |  |  | phase-0
0 | Idempotency | provider_message_id unique; insert-on-conflict-ignore | High | 9 |  |  | phase-0
0 | Deploy | Single-VPS all-in-one for pilot; Supabase managed | High | 8.5 |  |  | phase-0
0 | Mechanisms | SQL migrations+runner; withClinicContext; bootstrap; liveness/readiness; Vault boot; webhook handshake | High | 8.5 |  |  | phase-0
1A | KB | Unified substrate (manual + doc chunks); rules always-injected; 0.70; text-layer ingestion | High | 8.5 |  |  | phase-1a
1A | Pipeline | 5 intents; ordered gate chain (takeover→safety→confidence→intent); decision-token outbound | High | 9 |  |  | phase-1a
1A | Prompt | role→rules→KB→contract; ~10 turns; fail-safe truncation; cacheable prefix | High | 8.5 |  |  | phase-1a
1A | Window | Auto-reply as gate outcome; out-of-window hold→resend once→escalate; no templates in 1A | High | 8.5 |  |  | phase-1a
1A | Inbox | Modes bot/human/paused/resolved; explicit takeover; self-healing handback | High | 8.5 |  |  | phase-1a
1A | Audio | Transcription provider-abstracted (Deepgram default); fail→retype; repeat→handoff | High | 8.5 |  |  | phase-1a
1A | Safety | Minimal deflection guardrail (booking-only clinics); deterministic gate + injected rules | High | 8.5 |  |  | phase-1a
1A | Keys | Model A — Docmee-owned platform keys; provider/model = IA-Studio config; BYOK deferred | High | 8.5 |  |  | phase-1a
1B | Patient | Auto-created, clinic-scoped one-per-identity, progressively enriched, distinct from intake | High | 8.5 |  |  | phase-1b
1B | CRM | Built-in = panel patient profile + tags/statuses/notes/search; polish→2A/2C; export→3C | High | 8.5 |  |  | phase-1b
1B | Assignment | Shared queue + claim + auto-assign-on-takeover; auto-routing → 2A | High | 8.5 |  |  | phase-1b
1B | Tags/Status | Free-form multi-tags + light patient status; NO duplicate conversation-status (mode covers it) | High | 8.5 |  |  | phase-1b
1B | Notes | Patient-level internal notes primary (authored+timestamped); conversation notes secondary | High | 8.5 |  |  | phase-1b
1B | Search | Structured filters + patient-identity (HMAC) search; message-content search deferred (R12) | High | 8.5 |  |  | phase-1b
1B | Data capture | Bot extracts contact/CRM fields via tool-calling → validated DAL allowlist writes; confidence-gated (verified vs suggested); per-field source; secretary edits win | High | 8 |  |  | phase-1b
1B | Notifications | 1B slice: handoff/distress → urgent (panel+email), new lead → info (panel); priority-tagged (P1–P4 fwd-compatible); visible-until-acknowledged; clinic-level email config (recipients + per-event toggles); escalation/per-user prefs/quiet-hours/push → 2A/3D | High | 8.5 |  |  | phase-1b
1B | Sweep | Backfill resolve-or-create; patient timeline = conversation-list (no merged stream); bot-vs-bot newest-confident wins (staff>bot); assignment persists through resolve; RBAC enforced at API/DAL | High | 8.5 |  |  | phase-1b
1C | Calendar | Google Calendar = datetime source of truth + appointments row for the rest; availability = clinic schedule ∩ Google free/busy; Docmee primary writer; free/busy-at-booking + reconciliation; live two-way sync → Future Improvements (FI1); one calendar per clinic (per-doctor → 3A) | High | 8.5 |  |  | phase-1c
1C | Scheduling agent | 8-step resumable intake in patient_intake (collect service/name/slot); resume-on-interruption + mid-intake digression; re-validate availability on write (re-offer if taken); bot owns booking, secretary catches edges with intake context; reschedule/cancel → humans in 1C | High | 8.5 |  |  | phase-1c
1C | Appt lifecycle | States booked/confirmed/completed/cancelled/no-show + logged transitions; auto-completion sets state + fires 2C-bound hook; no-show manual; surfaced in profile+inbox; cancellation cascade mechanism built (calendar cancel + future automation kill); patient reminders → 2C | High | 8.5 |  |  | phase-1c
2A | Routing | Optional per-clinic strategy (shared-queue default / round-robin / load-based); presence-aware (route only to available; none available → shared queue + notify); on handoff + new conversation; never overrides explicit assignment; RBAC-gated. Robust presence + load-optimization → FI5/FI6 | High | 8.5 |  |  | phase-2a
2A | Notifications | Full system: P1–P4 driving differentiated channels/behavior; configurable escalation ladder (assignee→all staff→admin→IA Studio) stopping on ack (resolves routed-but-unack); dedup/collapse; per-user prefs + quiet hours with P1-safety breakthrough; panel + per-user email + basic web push (native push → 3D/FI4) | High | 8 |  |  | phase-2a
2A | Quick replies | Clinic-defined canned responses + variable interpolation (patient/clinic/slot); secretary-inserted (never auto-sent); category/shortcut; via outbound chokepoint; no AI-suggested replies in 2A | High | 9 |  |  | phase-2a
2A | IA Studio + RBAC | Platform-admin surface (clinic/plan/provider config, KB oversight, health, audited impersonation via Phase 0 acted_by seam); full 5-role matrix enforced at API/DAL; plan limits configured here, enforced in pipeline | High | 8.5 |  |  | phase-2a
2A | Invoicing | Manual subscription invoices (plan/amount/period GTQ/status) + simple doc + manual mark-paid; automated billing → FI5 | High | 8.5 |  |  | phase-2a
2B | Channels | Add Messenger + Instagram via Meta Graph API/webhooks behind the locked channel abstraction; per-clinic connect; inbound normalized + outbound via chokepoint; pipeline channel-agnostic (official APIs, no Evolution needed) | High | 8.5 |  |  | phase-2b
2B | Unified inbox | All channels in one inbox (channel badge per conversation); CRM/inbox channel-agnostic (1B); per-channel messaging-window rules enforced at outbound; bot replies identically across channels | High | 8 |  |  | phase-2b
2B | Identity merge | Manual merge only — secretary explicitly merges two patient records (audited, confirmation step); no auto-merge/auto-suggest (avoids PHI-mixing); smarter auto/suggested/reversible merge → FI6 | Manual (chosen) | 7.5 | Yes — approved | Cross-channel merge carries PHI-mixing risk (wrong merge blends two patients) and cross-channel signals are weak (IG/Messenger IDs ≠ phone). Hybrid auto-suggest rated 7.5; de-risked by choosing manual-only merge. | phase-2b
2C | Templates | Clinic templates (reminders/confirmations/follow-ups) with variables; draft→submitted→approved/rejected (Meta-synced), versioned; managed in IA Studio; templates = only out-of-window path; Messenger/IG use message tags | High | 8.5 |  |  | (pending record)
2C | Six-gate | Every proactive message passes 6 gates at the chokepoint: opt-out · approved-template · timing/eligibility · appointment-state-valid (cancellation cascade) · dedup/frequency-cap · clinic-enabled. Transactional-only scope | High | 8.5 |  |  | (pending record)
2C | Reminders | On booking, schedule reminder/confirmation jobs (BullMQ delayed); fire through six-gate; confirm-reply → booked→confirmed; cancellation/reschedule cancels/reschedules queued jobs (1C cascade gets its subscriber) | High | 8.5 |  |  | (pending record)
2C | Follow-ups | Automation engine subscribes to 1C auto-completion hook (+ no-show/cancel): completion → post-visit/review follow-up; no-show → recovery; template-gated via six-gate; per-clinic configurable (completes 1C seam) | High | 8.5 |  |  | (pending record)
2C | Broadcast | DEFERRED (locked) — broadcast/marketing deferred to FI8 (build later w/ explicit opt-in + marketing templates + frequency caps + number-reputation safeguards); 2C ships transactional-only | High | 8.5 |  |  | phase-2c
2D | Analytics | Metrics + QoS via scheduled rollup jobs into per-clinic aggregate tables (RLS): PR17 (totals, by-channel, leads, requests, scheduled, transfers, common Qs, peak hours, no-response, conversion) + PR32 (upset, abandoned, response times, no-closure, follow-up ops); dashboards in IA Studio + clinic panel | High | 8.5 |  |  | (pending record)
2D | Error review | Review queue fed by error_log + DLQ + events: unanswered, bot-asked-help, bad responses, handoffs, unknown intents, Meta/Calendar errors, failed messages; categorized + actionable (unanswered → KB-suggestion loop) | High | 8.5 |  |  | (pending record)
2D | Content search | Postgres full-text search (tsvector + GIN) over message content, strictly per-clinic (RLS) + audited; resolves R12 (deferred from 1B); semantic/pgvector search → FI | High | 8.5 |  |  | (pending record)
3A | Doctor entity | Activate dormant doctor seam (P0): clinic has 1..N doctors; per-doctor calendar/services/hours/FAQs. Doctor = bookable profile, optionally linked to a user account w/ doctor role. Single-doctor = N=1 default (backward compatible) | High | 8.5 |  |  | (pending record)
3A | Doctor selection | Extends locked 8-step intake: >1 doctor adds a selection step (explicit / specialty-inferred / 'any available' = earliest across doctors) then checks that doctor's calendar; single-doctor auto-skips | High | 8.5 |  |  | (pending record)
3A | Per-doctor KB | Retrieval is doctor-aware once a doctor context is set: clinic-shared chunks + selected-doctor chunks; rules always-injected; no cross-doctor leakage; pre-selection answers at clinic level / lists doctors | High | 8.5 |  |  | (pending record)
3A | Doctor routing | Conversations/appointments associate with a doctor; inbox filter by doctor; notifications route per-doctor-staffing or shared queue; doctor role sees own appts/convos (reuses 2A RBAC/routing) | High | 8 |  |  | (pending record)
3B | Flow builder | Declarative clinic-configurable flows (collect/ask/branch/tool/handoff) run by a deterministic engine; tool steps use DAL allowlist; guardrails always apply; versioned; starter library ships | High | 8 |  |  | (pending record)
3B | Advanced rules | Structured conditional rules (trigger/condition→enforced action) on top of always-injected text rules; safety-critical rules (payment-gate, after-hours, emergency-transfer) enforced deterministically at gates; tone = rule setting (resolves PR26/PR27) | High | 8.5 |  |  | (pending record)
3B | Secretary copilot | Panel-side staff copilot: reply drafting, summarization, KB-answer surfacing, suggested actions; same LLM+KB; human-in-the-loop (approve/edit before send); never messages patients autonomously | High | 8 |  |  | (pending record)
3C | OCR ingestion | Extend ingestion with provider-abstracted OCR (scanned PDFs/images) + docx/structured parsers; same chunk→embed→KB path; low-confidence OCR flagged for review; per-clinic | High | 8.5 |  |  | (pending record)
3C | Sheets/CRM export | Outbound integration: Google Sheets append + generic webhook/CRM connector; per-clinic mapping + encrypted creds; event-triggered or scheduled; clinic-authorized fields only (PHI egress audited) | High | 8 |  |  | (pending record)
3C | Automated reports | Reporting scheduler renders 2D analytics into periodic reports (PDF/email/Sheet) per-clinic cadence; reuses analytics rollups + email; clinic-scoped aggregates | High | 8.5 |  |  | (pending record)
3D | PWA | Next.js panel (already responsive) gains PWA: installable, manifest, service worker (cache + push); native iOS/Android stays FI4; one codebase | High | 8.5 |  |  | (pending record)
3D | Push | Web Push (VAPID) for PWA/browser wired into the notification/escalation ladder (1B/2A); per-user device subscriptions; preference-controlled; email fallback | High | 8.5 |  |  | (pending record)
3D | Mobile parity | PWA exposes secretary daily-driver ops (view/reply, take control, bot pause/activate, patient details, appointments, confirm, alerts, notes) via responsive panel; deep admin stays desktop | High | 8.5 |  |  | (pending record)
2A | Panel i18n | Closes PR21 GAP — Spanish + English panel i18n: i18n framework from the start (keys + per-user locale switch) across IA Studio + clinic panel, menus, statuses, alerts, reports; panel language independent of chatbot; ES+EN at launch | High | 8.5 |  |  | gap-closure
1A | Chatbot i18n | Closes PR22 (amends 1A) — Spanish + English chatbot: detect patient language, respond in it using only clinic-approved info; ES+EN at launch; further languages → FI | High | 8.5 |  |  | gap-closure
1C | Bot appt status | Closes PR09 (amends 1C) — bot answers 'is my appointment confirmed?' by reading Calendar (not-found → human); reschedule/cancel DELIBERATELY stay human-routed for safety; bot-driven reschedule/cancel → FI7 | High | 8.5 |  |  | gap-closure
0 | Retention | Configurable per-clinic data retention w/ market-standard defaults (messages ~24mo, configurable 6–36mo; patient records while active), bounded by compliant floors; soft-delete → scheduled hard-purge cascade (messages/media/embeddings/exports, audited); right-to-erasure wired to opt-out chokepoint; GDPR storage-limitation + erasure baseline | High | 8.5 |  |  | cross-cutting
0 | Observability | Lean single-VPS platform monitoring: Sentry (errors/traces) + /health endpoint + external uptime/synthetic checks on critical path (webhook→reply) + Bull Board (queue health) + host metrics (Netdata/Grafana Agent) + alerting (VPS down/queue backlog/webhook failures/TLS expiry); distinct from 2D clinic-facing error review | High | 8.5 |  |  | cross-cutting
0 | Compliance | Design to GDPR-style baseline (explicit consent, sensitive/health-data handling, retention limits, erasure, breach response) — safe superset of current Guatemalan law (no comprehensive PDP law yet; Decree 57-2008 criminalizes commercializing personal data w/o consent; Health Code protects health data; Initiative 6,105 pending). Never commercialize patient data; written consent for any export (ties SEC24); local-counsel review before launch (X20) | High | 8.5 |  |  | cross-cutting

## Update Log (hidden)
Date | Ref | Note
2026-06-13 | Build Backlog | Added Build Backlog tab + docmee-build-backlog.md — sequenced from sealed plan: Sprint 0 (unblock Meta/counsel + SEC06) → Phase 0 → 1A–1C → Pilot launch gate → 2A–3D. Each stage carries its gates/gaps/actions/security. Two test layers (RLS, six-gate) flagged to build in-phase, not post-deploy
2026-06-13 | Main confidence | Added live Confidence section to Main dashboard (Phase 0→3D): total scored, average, lowest, and counts by tier (≥9 / 8.5 / 8.0 / <8) via COUNTIF on the Decisions Index score column; flags the one sub-8 (2B identity merge 7.5) + the 8.0 watch list
2026-06-13 | Cross-cutting locked | Closed the 4 potential-misses: LOCKED retention/erasure (D62, configurable + GDPR baseline), platform observability (D63, lean single-VPS), GDPR-baseline compliance (D64, per Guatemala law check — Decree 57-2008 + Health Code + Initiative 6,105). Gaps G62–G63. Security SEC25. Testing/QA → action X19 (non-blocking, post-deploy). Legal counsel → action X20
2026-06-13 | ALL 12 PHASES SEALED | Broadcast locked = DEFERRED to FI8 (2C transactional-only). 2C sweep G57–G61 locked (timezone, confirm-reply, template-rejection, frequency-cap, failed-send idempotency). Formally sealed 2C,2D,3A,3B,3C,3D → all 12 phases sealed. Planning phase complete; next step is build. Decisions finalized — gates/actions remain for implementation
2026-06-13 | Gap-closure locked | Locked recommendations for the 3 requirement gaps — PR21 ES+EN panel i18n (8.5), PR22 ES+EN chatbot (8.5), PR09 bot appt-status query (8.5; reschedule/cancel stay human, bot-driven → FI7). PR21 GAP→Planned, PR22 Partial→Planned. Requirements Partial/Gap now 1 (PR09 by design). Added FI7
2026-06-13 | 3D Q1–Q3 | Mobile/PWA/Push locked — PWA delivery (8.5), Web Push/VAPID into notification ladder (8.5), mobile parity for secretary ops (8.5). Sweep G52–G56 locked. PR23 PWA path locked (native=FI4), PR24 push locked. No flags
2026-06-13 | Roadmap complete | All 12 phases now have decisions locked (0,1A,1B,1C,2A,2B,2C,2D,3A,3B,3C,3D). Remaining open: 2C Q5 broadcast (parked) + 3 requirement gaps (PR21 panel i18n, PR22 English chatbot, PR09 bot reschedule/cancel+status). Formal phase seals pending
2026-06-13 | Gap inventory (all) | Full gap log — Gaps tab holds G01–G51, all Locked/Resolved. By phase: P0/1A/1B/1C foundation+sweeps G01–G25 · 2A G26–G28 · 2B G29–G31 · 2D G32–G36 · 3A G37–G41 · 3B G42–G46 · 3C G47–G51. Requirement gaps tracked separately on Platform Requirements (remaining: PR21 panel i18n GAP, PR22 English chatbot, PR09 bot reschedule/cancel — all surfaced on Main)
2026-06-13 | 3C Q1–Q3 | Integrations & OCR locked — OCR/rich-format ingestion (8.5), Sheets/CRM export (8.0), automated reports (8.5). Sweep G47–G51 locked. Added X18 (Sheets/CRM connect) + SEC24 (external data egress). PR25 Covered (OCR), PR31 export locked. No flags
2026-06-13 | 3B Q1–Q3 | Advanced Intake locked — declarative custom-flow builder (8.0), structured advanced rules w/ deterministic safety enforcement (8.5), human-in-the-loop secretary copilot (8.0). Sweep G42–G46 locked. Closed requirement gaps PR26/PR27/PR28 (Partial→Planned). No flags
2026-06-13 | 3A Q1–Q4 | Multi-Doctor locked — doctor entity/per-doctor config (8.5), doctor selection in intake (8.5), per-doctor KB scoping (8.5), per-doctor routing/visibility (8.0). Sweep G37–G41 locked. Added X17 (per-doctor calendar connect). Activates the P0 doctor seam; N=1 backward compatible. No flags
2026-06-13 | 2D Q1–Q3 | Analytics & Search locked — metrics+QoS rollups (8.5), error review area (8.5), per-clinic full-text message search (8.5, resolves R12). Sweep G32–G36 locked. No flags. 2D decisions complete (formal seal alongside 2C)
2026-06-13 | Q5 → pending | Broadcast/marketing set to PENDING (parked) per user — not a blocker; transactional 2C unaffected; revisit before sealing 2C. Main KPI now 'Decisions parked (revisit)'
2026-06-13 | Hide tabs (opt 2) | Hid all sheets except Main per request — only the dashboard shows in the tab bar. Nav links replaced with a static tab directory + unhide instructions (Excel can't hyperlink to hidden sheets). To open a sheet: right-click Main tab ► Unhide
2026-06-13 | Main dashboard | Added Main home tab (first, opens by default) — live KPI cards (phases sealed, decisions, flagged, risks, security, requirements, hours, AI uses, cost), one-click navigation to every tab, and an open-items list. Improved both Gantts (0–26 week axis, gridlines, titles, thicker bars). Tabs kept visible so nav links work (hidden tabs can't be hyperlink targets without macros)
2026-06-13 | Cost actuals | Logged this session's AI-assisted work as ESTIMATES — 2C decisions (1.5 hrs / 6 uses) + cross-cutting PM/tracker line (3.5 hrs / 18 uses). Added PM row to cost table. Figures are estimates to be overwritten with real hours + real per-use cost
2026-06-13 | Cost Tracker | Added Cost Tracker tab — deliverables (12 phases) vs. weeks/est-hrs/actual-hrs, dev cost, AI-assistant uses + cost, live totals. Editable assumption inputs: dev rate $/hr, AI cost per use, hours/week. All costs are live formulas
2026-06-13 | Charts + font | Converted column bar chart to Gantt; added Requirements Gantt (PR01–PR32 mapped to delivering phase, plotted on the 26-week timeline); dark-styled all charts (dark plot area, light axis/title/legend text). Normalized to a single uniform light font across every tab for readability
2026-06-13 | Dark mode | Restyled workbook to dark theme — dark cell/page backgrounds, light text, darkened status/priority/coverage palettes, gridlines off, dark tabs
2026-06-13 | Platform Reqs | Added Platform Requirements tab (PR01–PR32) cross-checking the spec PDF vs our build. ~18 Covered, ~6 Partial, ~7 Planned, 1 Gap. Surfaced: panel i18n GAP (PR21), English chatbot deferred (PR22), bot reschedule/cancel + appt-status-query routed to humans (PR09)
2026-06-13 | 2C Q1–Q4 | Automation locked — templates+approval (8.5), six-gate proactive model (8.5), reminders/confirmations + cancellation-cascade subscriber (8.5), post-visit follow-ups via auto-completion hook (8.5). Q5 BROADCAST/marketing flagged for decision (defer / basic-in-2C / later). Added SEC23
2026-06-13 | Overview fix | Phase status table now lists ALL 12 phases (was bundling 2C–3D); fixed table/summary overlap; completed live counts (added Blocked/waiting, Phases-sealed, Security-open). Confirmed counts are live COUNTIF, recomputed each run
2026-06-13 | Security Audit | Added Security Audit tab (SEC01–SEC22) — cyber/app/database/infra/compliance concerns with details, blast radius, priority, recommended solution, status. 2 Critical, ~10 High; 5 items Open (SEC06 LLM-PHI, SEC14 backups, SEC16 PHI-in-logs, SEC18 rate-limit, SEC22 supply-chain)
2026-06-13 | Pros/Cons desc | Added a short Description column to Pros and Cons tabs (per-decision one-line summary)
2026-06-13 | Decisions Index | Added Score /10 + Flagged + 'Reason if < 8' columns; sub-8 manually-approved decisions shown in RED with their as-presented score and the reason for the low rating (2B Identity merge 7.5)
2026-06-13 | 2B SEAL | Phase 2B sealed — Q1 channels (8.5), Q3 unified inbox (8.0), Q2 cross-channel merge = MANUAL only (user decision; recorded as con D37 + improvement FI6) + sweep G29–G31. R11 mitigated. See phase-2b-channels-decisions.md
2026-06-13 | 2B Q1/Q3 | Channels locked — Messenger+IG via Meta Graph API behind channel abstraction (Q1, 8.5); unified cross-channel inbox + per-channel window rules (Q3, 8.0). Q2 cross-channel identity MERGE flagged (7.5 <8) for decision (hybrid / manual-only / defer). Added X16 (per-clinic Messenger/IG connect)
2026-06-13 | 2A SEAL | Phase 2A sealed — Q1 routing, Q2 notifications+escalation, Q3 quick replies, Q4 IA Studio+RBAC, Q5 manual invoicing + sweep G26–G28. All ≥8 confidence (auto-lock). FI5 added (automated billing). See phase-2a-multiuser-decisions.md
2026-06-13 | 2A Q2 | Notifications + escalation locked — P1–P4 differentiated behavior; configurable escalation ladder (ack stops it; resolves routed-but-unack); dedup; per-user prefs + quiet hours (P1 breaks through); panel + per-user email + basic web push (native → 3D/FI4)
2026-06-13 | Progress tab | Added Progress dashboard — phase Gantt (with progress shading), development-progress chart, deployment/external-actions chart, overall-project doughnut; live charts. Fixed Closed COUNTIF wildcard
2026-06-13 | Pros/Cons tabs | Added Pros and Cons tabs (D01–D30, all recorded decisions) with a Category column (Architecture/Security/Compliance/Deployment/Development/Product/AI/Data/Integration/Cost/Safety/Ops); reverted Future Improvements to FI1–FI4
2026-06-13 | 2A Q1 | Routing locked — optional per-clinic (shared-queue default / round-robin / load-based), presence-aware, on handoff + new conversation, never overrides explicit assignment, RBAC-gated. Tradeoffs (presence, load-count) recorded in Cons tab; routing×escalation overlap resolved in Q2
2026-06-13 | 1C SEAL | Phase 1C sealed — Q1–Q3 + 7 sweep locks (G19–G25: calendar-outage handoff, double-write integrity, timezone read-back, reschedule-in-Docmee, booking guardrails, slot re-validate, booking horizon) + acceptance gate. See phase-1c-scheduling-decisions.md
2026-06-13 | Gaps tab | Added Gaps tab — all 25 sweep-surfaced gaps across Phases 0/1A/1B/1C (G01–G25); all locked (G24 resolved by Q2 re-validate-on-write)
2026-06-13 | 1C Q3 | Appointment lifecycle locked — states booked/confirmed/completed/cancelled/no-show + logged transitions; auto-completion sets state + 2C-bound hook; no-show manual; surfaced in profile+inbox; cancellation cascade mechanism built (reminders → 2C)
2026-06-13 | 1C Q2 | Scheduling agent + intake locked — 8-step resumable patient_intake (service/name/slot); resume + mid-intake digression; re-validate-on-write (re-offer if taken); bot owns booking, reschedule/cancel → humans in 1C
2026-06-13 | 1C Q1 | Calendar integration locked — Google Calendar = datetime truth + appointments row; availability = clinic schedule ∩ Google free/busy; Docmee primary writer; free/busy-at-booking + reconciliation. Live two-way sync FLAGGED as future improvement (FI1). Added X15 (per-clinic Calendar connect + availability config)
2026-06-13 | 1B SEAL | Phase 1B sealed — Q1–Q4 + 5 sweep locks (backfill, patient timeline, bot-vs-bot precedence, assignment×mode, RBAC enforcement) + acceptance gate. See phase-1b-human-inbox-decisions.md
2026-06-13 | 1B Q4 | Notifications (1B slice) locked — handoff/distress→panel+email, new-lead→panel, priority-tagged, visible-until-acknowledged; ADDED clinic-level email configurability (recipients + per-event toggles); escalation/prefs/quiet-hours/push → 2A/3D
2026-06-13 | 1B Q3 | Patient data capture locked — bot extracts contact/CRM fields via tool-calling → validated DAL writes; confidence-gated (verified vs suggested); per-field source + secretary-edits-win. R13 added (extraction accuracy)
2026-06-13 | 1B Q2 | Inbox organization locked — shared queue + claim (routing→2A); tags + light patient status (no duplicate conversation-status); patient-level notes; filters + identity search; message-content search deferred (R12)
2026-06-13 | 1B Q1 | Patient model locked (auto-created, clinic-scoped, progressively enriched); built-in CRM = panel profile; R11 added (cross-channel dupes → 2B)
2026-06-13 | 1A SEAL | Phase 1A sealed — Q1–Q3 + audio + deflection + 5 operational locks + acceptance gate
2026-06-13 | 1A Q3 | Inbox + bot-mode + self-healing handback; transcription as swappable block; Convocore not a transcription provider
2026-06-13 | 1A Q2 | Intent set; layered routing + gate ordering; booking→handoff; deflection safety; prompt assembly; auto-reply + 24h window (hold→resend→escalate)
2026-06-13 | 1A Q1 | KB content model + text-layer document ingestion; R9 added; X5/X11 updated
2026-06-13 | Keys | Model A — Docmee-owned platform keys locked
2026-06-13 | R10/X14 | Reduced to minimal deflection guardrail (booking-only clinics)
2026-06-13 | 0 SEAL | Phase 0 sealed — 10 core + 2 sweep + 6 mechanism gaps + acceptance gate
2026-06-13 | R8/X12 | Single-VPS SPOF; backups required before real patients
2026-06-13 | X13 | Redundancy/HA parked (trigger: first real patients / SLA)
2026-06-13 | R4/R5 | De-risked & locked (separate stable HMAC key; withAdminContext guarded door)
2026-06-13 | X2/X9/X10 | Evolution interim bridge adopted; R7 added
2026-06-13 | X8 | Encryption key source closed (Supabase Vault + envelope + key_version)
2026-06-13 | Init | Trackers created

## Future Improvements (hidden)
ID | Improvement | Context / source | Trigger — when to build | Notes
FI1 | Real-time two-way Google Calendar sync (live push/webhook → update Docmee on external edits/deletes) | Flagged at 1C Q1 (1C ships free/busy-at-booking + reconciliation only) | Clinics heavily managing appointments directly in Google Calendar; post-1C release | Calendar stays datetime source of truth; removes reconciliation lag
FI2 | Self-hosted LLM (e.g., RunPod) for cost optimization | Architecture future mode (rollout-3) | When LLM spend justifies / data-residency push | Gateway already provider-abstracted — swap, not rebuild
FI3 | Commercial license control + self-hosted deployment (Ed25519 license server, Tauri installer, control plane) | Architecture future modes | When selling self-hosted / white-label installs | Soft-enforcement contract still applies; placeholders only today
FI4 | Native mobile app | Architecture future (only if PWA insufficient) | If PWA proves inadequate for clinics | PWA + push is the planned 3D path first
FI5 | Automated billing / payment gateway (e.g. Stripe) + dunning | From 2A Q5 — 2A ships manual invoicing only | When clinic count makes manual invoicing impractical | Plan model already defined; this automates charge + collection
FI6 | Smarter cross-channel identity merge (verified auto-link on strong signals + duplicate suggestions + reversible merge) | From 2B Q2 — 2B ships manual merge only | When cross-channel duplicates become common / a reliable signal source exists | Reduces manual merge effort; must preserve PHI-mixing safety
FI7 | Bot-driven reschedule / cancel via Calendar (guardrailed: confirmation + ownership checks + cancellation cascade) | From PR09 gap-closure — bot does status-query now; reschedule/cancel stay human for safety | Once bot reliability is proven and guardrails validated | Spec wants bot reschedule/cancel; deferred deliberately — 1C routes these to humans
FI8 | Broadcast / marketing campaigns (promotional messages to patient lists) with explicit marketing opt-in + marketing templates + frequency caps + number-reputation safeguards | From 2C Q5 — 2C ships transactional-only | When promotional outreach is needed and opt-in consent infra is in place | Higher compliance/spam/number-ban risk — must be consent-gated + rate-limited

## Gaps (hidden)
ID | Phase | Gap (surfaced in sweep) | Resolution / decision | Status
G01 | 0 | Migration tooling unspecified (how migrations run) | Raw numbered SQL + minimal forward-only runner + schema_migrations; transactional apply | Locked
G02 | 0 | RLS context chokepoint — how clinic context is ALWAYS set | withClinicContext() helper; raw pool private to packages/db; API preHandler + worker wrapper; single audited admin path | Locked
G03 | 0 | First clinic/admin bootstrap (chicken-and-egg; no public signup) | Operator-run bootstrap seeds first platform admin (random pw, force-rotate); clinics via real create-clinic/invite-admin | Locked
G04 | 0 | Health-check depth (what 'green' verifies) | /health liveness + /health/ready (Postgres+Redis+Vault; external providers excluded; ~5s cache); gate uses readiness | Locked
G05 | 0 | Secrets bootstrapping order (Vault circularity) | Env = connection secrets only; master key fetched from Vault at boot; host-secret-store fallback; fail-fast to not-ready | Locked
G06 | 0 | Webhook verification handshake (subscribe before messages) | Meta GET verify-challenge (constant-time) + HMAC POST + Evolution adapter registration | Locked
G07 | 0 | Deployment target undefined | Single-VPS all-in-one for pilot; Supabase managed; redundancy → FI/X13 | Locked
G08 | 0 | Elevated-impersonation attribution seam | Reserve nullable acted_by_platform_user_id now (empty in 0); behavior built 2A | Locked
G09 | 1A | Conversation lifecycle (new vs continue) | >30 days → new conversation; resolved + inbound <7 days → reopen in bot mode; history uses current conversation | Locked
G10 | 1A | Bot disclosure to patient | One-time lightweight disclosure in first bot reply of a new conversation; per-clinic, on by default | Locked
G11 | 1A | Outbound length / WhatsApp formatting | Brevity in answer contract + split >4096 chars on paragraph boundaries (≤2–3 msgs); WhatsApp-supported formatting | Locked
G12 | 1A | Embedding-job failure path | Retry w/ backoff → mark chunk failed + flag doc 'ingestion incomplete' + log/DLQ; others unaffected | Locked
G13 | 1A | Provider outage / rate-limit mid-message | Bounded retries → fail-safe handoff + holding message; DeepSeek down → low-confidence fallback; embedding down → handoff | Locked
G14 | 1B | patient_id backfill mechanics | Forward-only resolve-or-create on inbound + one-time idempotent backfill grouping conversations by identity | Locked
G15 | 1B | Patient timeline aggregation | Profile = conversation-list + patient data/tags/notes; no merged cross-conversation message-stream (R12) | Locked
G16 | 1B | Bot-vs-bot data correction over time | Newest high-confidence bot capture updates older bot field; never overrides staff; precedence staff>newest-bot>older-bot>suggested | Locked
G17 | 1B | Assignment × bot-mode edges | Assignment persists through resolve (last-owner); active queue = human/unresolved; reassign allowed | Locked
G18 | 1B | RBAC enforcement in inbox/profile/notes | Implements locked 5-role matrix at API/DAL (not UI-only); internal notes staff-roles-only | Locked
G19 | 1C | Calendar OAuth failure / API outage mid-booking | Fail-safe handoff + holding message; clinic alert + 'Calendar disconnected' state; bounded retry | Locked
G20 | 1C | Double-write integrity (Calendar event vs appointments row) | Write event first → row; on row-fail best-effort delete event → handoff; reconciliation backstop | Locked
G21 | 1C | Timezone + relative-time correctness | Clinic-local compute, UTC store, tz library for DST; read-back absolute local datetime at confirmation | Locked
G22 | 1C | Reschedule/cancel-via-secretary mechanics | Docmee canonical: secretary edits in Docmee → rewrites Google event + logs; direct-Calendar edits reconciled (FI1) | Locked
G23 | 1C | Booking guardrails (opt-out / paused / after-hours) | Booking not gated by opt-out (inbound-initiated); 2C reminders are (six-gate); after-hours OK; paused follows mode rules | Locked
G24 | 1C | Slot-offer staleness | Already handled by re-validate-availability-on-write (Q2) | Resolved
G25 | 1C | Booking horizon + past-time guard | Configurable horizon (~60 days) + no-past-slots guard from availability computation | Locked
G26 | 2A | Plan conversation-limit enforcement | Soft-cap default: warn at threshold, keep serving (no mid-care cutoff), flag overage for billing; hard cutoff configurable | Locked
G27 | 2A | Quick-reply variable safety | Variables resolve server-side from current patient/conversation only; unresolved → blank, never guessed | Locked
G28 | 2A | IA Studio impersonation safety | Every impersonated action stamped acted_by_platform_user_id + audit log + time-boxed + platform-only | Locked
G29 | 2B | Per-channel media/attachment differences | Normalize supported types across channels; unsupported (IG story, sticker, etc.) → friendly notice or handoff | Locked
G30 | 2B | Channel-specific re-engagement vs WhatsApp templates | In-window replies normal; out-of-window proactive re-engagement (Messenger tags / IG / WA templates) → 2C; 2B follows locked hold-resend/escalate per channel | Locked
G31 | 2B | Channel token/connection failure | Mark channel disconnected + alert clinic + pause that channel's inbound + bounded retry (mirrors calendar/provider-outage pattern) | Locked
G32 | 2D | Analytics timezone correctness | Rollups bucket by clinic-local time (reuse locked tz handling); peak-hours/daily metrics per clinic timezone | Locked
G33 | 2D | Metrics PHI-safety | Aggregate tables store counts/derived flags only — no raw PHI; sentiment = derived label, not message text (ties SEC16) | Locked
G34 | 2D | Search clinic isolation | FTS strictly RLS-scoped per clinic; no cross-clinic results; queries audited (mirrors identity-search rule) | Locked
G35 | 2D | Error-review action loop | Unanswered/unknown-intent items become KB-entry suggestions; resolved items tracked so the same gap isn't re-surfaced | Locked
G36 | 2D | Analytics query performance | Precomputed rollups / materialized views + indexes; dashboards read aggregates, never heavy live scans of messages | Locked
G37 | 3A | Single-doctor backward compatibility | N=1 is the default; existing clinics unaffected; intake auto-skips doctor step; one implicit doctor owns current calendar/KB | Locked
G38 | 3A | Per-doctor calendar connection lifecycle | Each doctor's Google Calendar = separate connection (X17); disconnection handling mirrors per-clinic calendar/provider-outage pattern | Locked
G39 | 3A | 'Any-doctor' booking & availability conflicts | 'Any available' books earliest across selected doctors; per-doctor no-double-book reuses calendar-truth; ties chosen doctor to the appointment | Locked
G40 | 3A | Doctor deactivation / removal | Deactivating a doctor: future appointments reassign or cancellation-cascade; KB chunks archived; bot stops offering that doctor; history retained | Locked
G41 | 3A | Cross-doctor data isolation | A doctor's prices/hours/FAQs never surface for another; retrieval filtered by selected doctor (mirrors clinic-isolation rule) | Locked
G42 | 3B | Custom-flow validation | Clinic flows validated before activation: required terminal states, no infinite loops, only allowlisted tools/actions, mandatory guardrails auto-injected | Locked
G43 | 3B | Rule precedence / conflict resolution | Deterministic ordering; safety rules outrank preference rules; explicit conflict handling so rules can't deadlock or contradict silently | Locked
G44 | 3B | Safety-critical rule enforcement point | Payment-gate, after-hours, emergency-transfer enforced deterministically at pipeline gates (not LLM discretion); ties to medical-safety D16 | Locked
G45 | 3B | Secretary-copilot guardrails | Copilot output is draft-only, never auto-sent; KB-grounded; no cross-clinic PHI; suggestions audited | Locked
G46 | 3B | Flow/rule versioning & rollback | Flows + rules versioned per clinic; bad flow can be rolled back; all changes audited | Locked
G47 | 3C | OCR confidence / review | Low-confidence OCR flagged for human review before entering the KB; never silently ingest garbage text | Locked
G48 | 3C | External-export PHI safety & consent | Only clinic-authorized fields exported; per-clinic config; egress audited + revocable; logged (SEC24) | Locked
G49 | 3C | Integration credential security | Sheets/CRM OAuth tokens stored encrypted like Meta/Calendar tokens; rotation; per-clinic isolation | Locked
G50 | 3C | Export/report idempotency & retries | No duplicate rows/reports on retry; bounded retry; failures surfaced in the error-review area | Locked
G51 | 3C | Report PHI scoping | Reports contain clinic-scoped data only; aggregates where possible; access-controlled delivery | Locked
G52 | 3D | PWA offline behavior | Offline shell + graceful degradation; never show stale-as-live; queued actions clearly marked; no silent send failures | Locked
G53 | 3D | Push token lifecycle | Subscriptions registered/refreshed/revoked per device; expired pruned; no push after logout | Locked
G54 | 3D | iOS push limitations | Detect unsupported; require installed PWA on iOS; fall back to email/badge; set expectations | Locked
G55 | 3D | Push preferences / quiet hours | Reuse notification prefs + quiet hours; don't push P3/P4 overnight unless urgent | Locked
G56 | 3D | Mobile auth/session security | Same RBAC + session security on mobile; per-device session handling; biometric optional via browser | Locked
G57 | 2C | Automation timezone correctness | Reminders/confirmations/follow-ups fire in clinic-local time (reuse locked tz handling) | Locked
G58 | 2C | Confirm-reply handling | Patient reply to a reminder parsed: confirm → confirmed; cancel/reschedule → route to humans (1C policy) | Locked
G59 | 2C | Template-rejection handling | Meta rejects a template → clinic alerted + any automation using it paused until fixed | Locked
G60 | 2C | Frequency cap / anti-spam | Per-patient frequency cap across automations so multi-appointment patients aren't flooded (gate 5) | Locked
G61 | 2C | Failed proactive-send idempotency | Bounded retry on send failure; provider_message_id dedup prevents double-sends | Locked
G62 | 0 | Deletion / erasure cascade completeness | Erasure purges messages, media, embeddings, and flags prior exports; audited; backup handling per retention policy — no orphaned PHI | Locked
G63 | 0 | Consent capture for processing & export | Explicit consent recorded; any export requires consent (Decree 57-2008 criminalizes commercializing data w/o consent; ties SEC24); sensitive/health-data handled with care | Locked

## Pros (hidden)
ID | Phase | Category | Decision | Description | Pros
D01 | 0 | Security | Worker RLS | Background jobs run under per-clinic DB context; one audited admin path | Tenant isolation enforced at the DB for background jobs (not just API); single audited admin path
D02 | 0 | Security | Encryption | PHI encrypted at rest via app-layer envelope + rotating key | PHI encrypted at rest; app-layer envelope; key rotation via key_version
D03 | 0 | Security | Identities | Platform admins and clinic users are separate identity systems | Platform vs clinic users disjoint; clean privilege separation; impersonation audited
D04 | 0 | Architecture | Tenancy | Each user belongs to exactly one clinic (one-to-one) | Simple one-to-one user↔clinic; RLS isolation absolute
D05 | 0 | Compliance | Opt-out | Opted-out patients suppressed at a single outbound chokepoint | Compliance-grade outbound suppression at a single chokepoint; bot-irreversible
D06 | 0 | Architecture | Loop | Phase 0 builds pipes only — no automatic patient replies yet | Phase 0 ships pipes only; no premature auto-replies; safe foundation
D07 | 0 | Architecture | Idempotency | Redelivered webhooks de-duplicated via unique provider message id | Redelivered webhooks never double-process; exactly-once rows
D08 | 0 | Deployment/Ops | Deploy | Single all-in-one VPS for the pilot; managed Supabase | Single-VPS all-in-one — cheap, simple for the pilot
D09 | 0 | Development | Mechanisms | Migrations, context wrapper, bootstrap, health, secrets, webhook handshake specified | Migrations, context wrapper, bootstrap, health, secrets-boot, webhook handshake all specified — no ad-hoc gaps
D10 | 1A | Development | KB | Unified KB (manual + docs); rules always injected; 0.70 retrieval | Unified substrate (manual + docs); rules always-injected; grounded retrieval
D11 | 1A | Architecture | Pipeline | Ordered gate chain; reply needs a pipeline-issued decision token | Structurally-enforced gate ordering; reply can't emit without a decision token; safe by construction
D12 | 1A | AI/ML | Prompt | Deterministic prompt assembly with fail-safe truncation + cached prefix | Deterministic assembly + fail-safe truncation; cacheable prefix (cost)
D13 | 1A | Compliance | Window | Auto-reply within 24h; out-of-window hold→resend-once→escalate | Compliant auto-reply; out-of-window hold→resend-once→escalate; never silent
D14 | 1A | Product/UX | Inbox | Conversation modes + explicit takeover + self-healing handback | Clean takeover/handback; self-healing (no stuck-in-human); never speaks unprompted
D15 | 1A | AI/ML | Audio | Transcription is a swappable provider block (Deepgram default) | Provider-abstracted transcription; fail→retype→handoff
D16 | 1A | Safety | Safety | Minimal deflection guardrail for distress; clinics are booking-only | Minimal deflection guardrail; deterministic pre-LLM gate; booking-only scope
D17 | 1A | Cost/Business | Keys | Docmee-owned platform API keys (Model A); clinics never supply keys | Model A platform keys — zero clinic setup; matches plan billing; central rotation
D18 | 1B | Data | Patient | Patient auto-created on first contact, progressively enriched, clinic-scoped | Zero-friction auto-create; progressive enrichment; clean patient vs intake split
D19 | 1B | Product/UX | CRM | Built-in CRM is the panel profile + inbox; no external CRM needed | Built-in CRM = the panel; no external CRM required; functional in 1B
D20 | 1B | Product/UX | Assignment | Shared queue + claim + auto-assign on takeover | Shared-queue + claim fits small clinics; auto-assign-on-takeover
D21 | 1B | Product/UX | Tags/Status | Free-form tags + light patient status; mode covers conversation state | Free-form tags + light patient status; no duplicate conversation-status (mode covers it)
D22 | 1B | Product/UX | Notes | Patient-level internal staff notes, durable across conversations | Patient-level notes give durable CRM continuity
D23 | 1B | Data | Search | Filters + patient-identity search; message-content search deferred | Structured filters + identity (HMAC) search
D24 | 1B | AI/ML | Data capture | Bot fills CRM fields via tool-calling; secretary edits win | CRM self-populates; DAL-allowlisted; secretary-wins; source-tracked
D25 | 1B | Ops | Notifications | First notifications — handoff/distress + new lead via panel/email | Closes handoff-visibility loop; panel+email; clinic-level email config
D26 | 1B | Data | Sweep | Backfill, timeline, precedence, assignment, and RBAC operational locks | Backfill, timeline, bot-vs-bot precedence, assignment×mode, RBAC all pinned
D27 | 1C | Integration | Calendar | Google Calendar datetime truth ∩ free/busy availability; no double-book | No double-booking (schedule ∩ free/busy); clean source-of-truth split
D28 | 1C | AI/ML | Scheduling agent | Resumable 8-step booking intake; re-validate slot on write | Resumable intake survives messy WhatsApp; re-validate-on-write prevents double-book
D29 | 1C | Product/UX | Appt lifecycle | Appointment states + logged transitions + auto-completion hook for 2C | Auditable lifecycle; auto-completion hook for 2C; cancellation cascade mechanism
D30 | 2A | Ops | Routing | Optional presence-aware routing (shared-queue/round-robin/load-based) | Scales inbox to multi-secretary; optional (shared-queue default); presence-aware; reuses locked invariants
D31 | 2A | Ops | Notifications | Full P1–P4 notifications + escalation ladder + quiet hours + push | Completes 1B seam w/o rework; escalation ladder = can't-be-ignored safety net (closes routed-but-unack); dedup prevents alert fatigue; per-user prefs + push = real multi-user tool
D32 | 2A | Product/UX | Quick replies | Canned responses with variables, secretary-inserted, never auto-sent | Speeds + standardizes secretary replies; variables reduce typing; reuses outbound chokepoint
D33 | 2A | Security | IA Studio + RBAC | Platform-admin surface + full role-based panel access | Completes admin + RBAC seams; central clinic/plan/provider management; impersonation auditable
D34 | 2A | Cost/Business | Invoicing | Manual subscription invoicing (no payment gateway yet) | Charge clinics without building full billing; simple + fast
D35 | 2B | Integration | Channels | Adds Messenger + Instagram via official Meta Graph API | Channel abstraction already built for this; pipeline channel-agnostic; official Meta APIs (no Evolution for Messenger/IG); reuses chokepoint + idempotency
D36 | 2B | Product/UX | Unified inbox | All channels in one inbox; per-channel messaging-window rules | Unified staff experience; reuses channel-agnostic inbox/pipeline; window rules localized to outbound
D37 | 2B | Data | Identity merge | Manual cross-channel patient merge by staff (no auto-merge) | Resolves cross-channel dupes via deliberate staff action; avoids PHI-mixing risk of auto-merge; audited
D38 | 2C | Compliance | Templates | Clinic message templates with Meta approval lifecycle | Enables compliant out-of-window proactive messaging; tracked approval lifecycle; versioned + variables
D39 | 2C | Compliance | Six-gate | Six-gate compliance check before any proactive message | Compliance-grade proactive messaging; reuses opt-out chokepoint; cancellation cascade plugs into gate 4
D40 | 2C | Product/UX | Reminders | Scheduled reminders/confirmations; cancellation kills queued jobs | Drives confirmations + reduces no-shows; cancellation cascade finally gets a subscriber; reuses BullMQ delayed jobs
D41 | 2C | Product/UX | Follow-ups | Post-visit follow-ups subscribing to the completion hook | Completes 1C auto-completion seam; drives re-engagement/reviews; per-clinic configurable
D42 | 2D | Analytics | Analytics | Metrics & QoS via per-clinic rollup tables | Actionable metrics for clinics + platform; rollups keep queries fast; per-clinic isolated
D43 | 2D | Ops | Error review | Error/review queue with KB-improvement loop | Closes the quality loop (failures → KB/agent fixes); central visibility of bot/agent/API errors
D44 | 2D | Data | Content search | Per-clinic full-text message search (resolves R12) | Staff can find past messages; tsvector is cheap + built-in; per-clinic RLS contains PHI
D45 | 3A | Architecture | Doctor entity | Multi-doctor entity: per-doctor calendar/services/hours/FAQs | Reuses P0 seam + calendar integration per doctor; backward compatible (N=1); profile-vs-user split is flexible
D46 | 3A | Product/UX | Doctor selection | Doctor-selection step added to the booking intake | Natural extension of locked intake; specialty routing + 'any available' convenience
D47 | 3A | AI/ML | Per-doctor KB | Doctor-aware KB retrieval with cross-doctor isolation | Accurate per-doctor answers; reuses unified KB + retrieval; strict isolation
D48 | 3A | Product/UX | Doctor routing | Per-doctor conversation/appointment routing & visibility | Reuses 2A routing/RBAC; doctor visibility + per-doctor inbox filtering
D49 | 3B | Architecture | Flow builder | Declarative custom-flow builder + engine | Huge flexibility without code; reuses intake engine + DAL allowlist + guardrails; per-clinic + versioned
D50 | 3B | Architecture | Advanced rules | Structured conditional rules; deterministic safety enforcement | Makes safety-critical rules deterministic (not LLM-trusted); resolves PR26/PR27; per-clinic
D51 | 3B | AI/ML | Secretary copilot | Human-in-the-loop secretary copilot in the panel | Productivity for staff; reuses LLM+KB; human-approved (safe)
D52 | 3C | AI/ML | OCR ingestion | OCR + rich-format document ingestion into the KB | Unlocks scanned clinic docs; reuses ingestion+embedding; provider-abstracted OCR (swappable)
D53 | 3C | Integration | Sheets/CRM export | Outbound Sheets/CRM export of lead/patient data | Clinic data portability; reuses event stream; generic webhook = many CRMs
D54 | 3C | Analytics | Automated reports | Scheduled automated reports from 2D analytics | Hands-off clinic reporting; reuses 2D analytics + email; configurable cadence
D55 | 3D | Architecture | PWA | PWA delivery of the panel (installable, service worker) | One codebase (no native maintenance); installable + push without app stores; reuses panel
D56 | 3D | Product/UX | Push | Web Push (VAPID) alerts wired into the notification ladder | Real-time mobile alerts; standards-based (VAPID); reuses notification ladder
D57 | 3D | Product/UX | Mobile parity | Mobile parity for secretary daily-driver operations | Secretaries get a real mobile daily-driver; no separate reduced app to maintain
D58 | 2A | Product/UX | Panel i18n | Spanish+English panel internationalization (closes PR21) | Meets spec PR21; framework-first avoids a painful retrofit; per-user locale switch
D59 | 1A | AI/ML | Chatbot i18n | Spanish+English patient-facing chatbot (closes PR22) | Meets spec PR22; cheap with the LLM (detection + prompt); grounded per clinic KB
D60 | 1C | Product/UX | Bot appt status | Bot appointment-status query; reschedule/cancel kept human (closes PR09, FI7) | Bot handles low-risk status queries (spec PR09); reschedule/cancel stay human = safer; clear escalation
D61 | 2C | Compliance | Broadcast | Broadcast/marketing deferred to FI8 (2C transactional-only) | Avoids spam/number-reputation risk; keeps 2C focused on transactional; opt-in path preserved via FI8
D62 | 0 | Compliance | Retention | Configurable patient-data retention + right-to-erasure cascade | Market-standard configurable retention + erasure; not a medical record so shorter retention defensible; reuses encryption/RLS spine
D63 | 0 | Deployment/Ops | Observability | Lean single-VPS platform observability + alerting | Catches platform failures fast (errors, queue backlog, downtime, cert expiry); lean + cheap for single-VPS
D64 | 0 | Compliance | Compliance | GDPR-baseline compliance (Guatemala law + Initiative 6,105) | GDPR baseline satisfies current Guatemalan criminal/consent rules + future-proofs for Initiative 6,105; reinforces export-consent

## Cons (hidden)
ID | Phase | Category | Decision | Description | Cons / tradeoffs
D01 | 0 | Security | Worker RLS | Background jobs run under per-clinic DB context; one audited admin path | Every worker must set clinic context — mitigated by withClinicContext() wrapper + lint
D02 | 0 | Security | Encryption | PHI encrypted at rest via app-layer envelope + rotating key | Encrypted fields not SQL-searchable → HMAC lookup keys needed (R4)
D03 | 0 | Security | Identities | Platform admins and clinic users are separate identity systems | Two identity systems to maintain
D04 | 0 | Architecture | Tenancy | Each user belongs to exactly one clinic (one-to-one) | Won't fit clinic-group customers without a migration (R6)
D05 | 0 | Compliance | Opt-out | Opted-out patients suppressed at a single outbound chokepoint | Opt-out must be checked on every outbound (enforced structurally)
D06 | 0 | Architecture | Loop | Phase 0 builds pipes only — no automatic patient replies yet | No user-visible behavior in Phase 0 (acceptable — foundation)
D07 | 0 | Architecture | Idempotency | Redelivered webhooks de-duplicated via unique provider message id | Requires provider_message_id uniqueness handling
D08 | 0 | Deployment/Ops | Deploy | Single all-in-one VPS for the pilot; managed Supabase | Single point of failure (R8); redundancy deferred (X13)
D09 | 0 | Development | Mechanisms | Migrations, context wrapper, bootstrap, health, secrets, webhook handshake specified | More upfront plumbing before features
D10 | 1A | Development | KB | Unified KB (manual + docs); rules always injected; 0.70 retrieval | Document ingestion expands 1A scope (R9 — top schedule risk)
D11 | 1A | Architecture | Pipeline | Ordered gate chain; reply needs a pipeline-issued decision token | Single-entry discipline adds indirection
D12 | 1A | AI/ML | Prompt | Deterministic prompt assembly with fail-safe truncation + cached prefix | Truncation edge handling adds complexity
D13 | 1A | Compliance | Window | Auto-reply within 24h; out-of-window hold→resend-once→escalate | TTL tuning; held replies can go stale (mitigated by escalate)
D14 | 1A | Product/UX | Inbox | Conversation modes + explicit takeover + self-healing handback | Thin inbox in 1A; full features deferred to 1B
D15 | 1A | AI/ML | Audio | Transcription is a swappable provider block (Deepgram default) | Abstraction is extra (built lean, Deepgram first); extraction imperfect
D16 | 1A | Safety | Safety | Minimal deflection guardrail for distress; clinics are booking-only | Not clinical triage (by design); needs clinic wording sign-off (X14)
D17 | 1A | Cost/Business | Keys | Docmee-owned platform API keys (Model A); clinics never supply keys | Docmee bears LLM cost/usage exposure; BYOK deferred
D18 | 1B | Data | Patient | Patient auto-created on first contact, progressively enriched, clinic-scoped | patient_id backfill onto 1A conversations; cross-channel dupes (R11)
D19 | 1B | Product/UX | CRM | Built-in CRM is the panel profile + inbox; no external CRM needed | Advanced CRM polish deferred (2A/2C)
D20 | 1B | Product/UX | Assignment | Shared queue + claim + auto-assign on takeover | No auto-routing in 1B (→2A)
D21 | 1B | Product/UX | Tags/Status | Free-form tags + light patient status; mode covers conversation state | Patient-status taxonomy needs clinic defaults
D22 | 1B | Product/UX | Notes | Patient-level internal staff notes, durable across conversations | Conversation-level notes secondary in 1B
D23 | 1B | Data | Search | Filters + patient-identity search; message-content search deferred | No message-content search (encryption limit, R12 → ~2D)
D24 | 1B | AI/ML | Data capture | Bot fills CRM fields via tool-calling; secretary edits win | Extraction imperfect (R13); confirmation turns add friction
D25 | 1B | Ops | Notifications | First notifications — handoff/distress + new lead via panel/email | No escalation/preferences/quiet-hours in 1B (→2A)
D26 | 1B | Data | Sweep | Backfill, timeline, precedence, assignment, and RBAC operational locks | Patient timeline = conversation-list (no merged stream) in 1B
D27 | 1C | Integration | Calendar | Google Calendar datetime truth ∩ free/busy availability; no double-book | Live two-way sync deferred (FI1); per-clinic OAuth setup; free/busy API calls
D28 | 1C | AI/ML | Scheduling agent | Resumable 8-step booking intake; re-validate slot on write | No slot-hold (re-pick on busy calendars); reschedule/cancel → humans in 1C
D29 | 1C | Product/UX | Appt lifecycle | Appointment states + logged transitions + auto-completion hook for 2C | confirmed/no-show partly dormant until 2C; completion hook has no subscriber yet
D30 | 2A | Ops | Routing | Optional presence-aware routing (shared-queue/round-robin/load-based) | Presence is net-new (minimal in 2A); load-based needs a live open-assigned count
D31 | 2A | Ops | Notifications | Full P1–P4 notifications + escalation ladder + quiet hours + push | Heaviest 2A feature (many moving parts); web push net-new infra (service worker/VAPID); escalation timings need per-clinic tuning
D32 | 2A | Product/UX | Quick replies | Canned responses with variables, secretary-inserted, never auto-sent | Template-management UI + variable system to build; variable safety needs care (G27)
D33 | 2A | Security | IA Studio + RBAC | Platform-admin surface + full role-based panel access | Sizable admin surface; RBAC must be enforced at data layer + tested across surfaces
D34 | 2A | Cost/Business | Invoicing | Manual subscription invoicing (no payment gateway yet) | Manual effort; no automated dunning/payment (→ FI5)
D35 | 2B | Integration | Channels | Adds Messenger + Instagram via official Meta Graph API | Per-channel quirks (windows, attachments, IG rules); per-clinic Meta connection setup
D36 | 2B | Product/UX | Unified inbox | All channels in one inbox; per-channel messaging-window rules | Per-channel window/re-engagement differences add conditional logic (IG/Messenger tags vs WhatsApp templates)
D37 | 2B | Data | Identity merge | Manual cross-channel patient merge by staff (no auto-merge) | Manual effort; no auto-suggestions so dupes can persist unnoticed; single cross-channel view only when staff act; smarter/reversible merge deferred → FI6
D38 | 2C | Compliance | Templates | Clinic message templates with Meta approval lifecycle | Meta approval latency/rejection (clinic-owned R2/X4); per-channel divergence (templates vs message tags); template-management UI
D39 | 2C | Compliance | Six-gate | Six-gate compliance check before any proactive message | Six conditions add complexity; frequency-cap tuning; transactional-only scope (marketing separate)
D40 | 2C | Product/UX | Reminders | Scheduled reminders/confirmations; cancellation kills queued jobs | Job scheduling + cancellation coordination; reschedule must move jobs; confirm-reply parsing
D41 | 2C | Product/UX | Follow-ups | Post-visit follow-ups subscribing to the completion hook | Follow-up templates need approval; timing tuning; another automation surface
D42 | 2D | Analytics | Analytics | Metrics & QoS via per-clinic rollup tables | Aggregation jobs to build/maintain; sentiment/upset detection imperfect; dashboards to design
D43 | 2D | Ops | Error review | Error/review queue with KB-improvement loop | Another review surface; needs triage workflow; false-positive 'bad response' flags
D44 | 2D | Data | Content search | Per-clinic full-text message search (resolves R12) | Lexical only (no semantic) until FI; index maintenance; PHI exposure must stay clinic-scoped
D45 | 3A | Architecture | Doctor entity | Multi-doctor entity: per-doctor calendar/services/hours/FAQs | KB scoping (clinic vs doctor) complexity; each doctor connects own calendar; more config surface
D46 | 3A | Product/UX | Doctor selection | Doctor-selection step added to the booking intake | Intake step count grows; ambiguity when patient unsure; multi-calendar availability logic
D47 | 3A | AI/ML | Per-doctor KB | Doctor-aware KB retrieval with cross-doctor isolation | Chunk tagging by doctor; retrieval scoping; pre-selection ambiguity handling
D48 | 3A | Product/UX | Doctor routing | Per-doctor conversation/appointment routing & visibility | Optional per-doctor staffing config; routing complexity
D49 | 3B | Architecture | Flow builder | Declarative custom-flow builder + engine | Builder UX complexity; validating clinic-authored flows; execution determinism
D50 | 3B | Architecture | Advanced rules | Structured conditional rules; deterministic safety enforcement | Rule-engine complexity; condition language; precedence/conflict resolution
D51 | 3B | AI/ML | Secretary copilot | Human-in-the-loop secretary copilot in the panel | Another LLM surface (cost); UX integration; scope-creep risk
D52 | 3C | AI/ML | OCR ingestion | OCR + rich-format document ingestion into the KB | OCR cost+accuracy; table/layout extraction hard; low-confidence review step
D53 | 3C | Integration | Sheets/CRM export | Outbound Sheets/CRM export of lead/patient data | Per-clinic creds (X18); PHI egress (consent/security, SEC24); mapping config; external API reliability
D54 | 3C | Analytics | Automated reports | Scheduled automated reports from 2D analytics | Report rendering/templating; scheduling; PHI scoping (aggregates/clinic-scoped only)
D55 | 3D | Architecture | PWA | PWA delivery of the panel (installable, service worker) | iOS PWA caveats; no deep native integration; no app-store presence (native = FI4)
D56 | 3D | Product/UX | Push | Web Push (VAPID) alerts wired into the notification ladder | iOS push caveats; subscription/token management; best-effort delivery
D57 | 3D | Product/UX | Mobile parity | Mobile parity for secretary daily-driver operations | Responsive layout work for dense views; deep admin still desktop-first
D58 | 2A | Product/UX | Panel i18n | Spanish+English panel internationalization (closes PR21) | Translation upkeep for every new string; QA in two locales
D59 | 1A | AI/ML | Chatbot i18n | Spanish+English patient-facing chatbot (closes PR22) | EN answers need EN KB content or translation; language-detection edge cases
D60 | 1C | Product/UX | Bot appt status | Bot appointment-status query; reschedule/cancel kept human (closes PR09, FI7) | Spec also wanted bot reschedule/cancel — deferred to FI7 (partial vs spec)
D61 | 2C | Compliance | Broadcast | Broadcast/marketing deferred to FI8 (2C transactional-only) | No promotional outreach in v1; clinics wanting campaigns wait for FI8
D62 | 0 | Compliance | Retention | Configurable patient-data retention + right-to-erasure cascade | Cascade purge must be complete (messages/media/embeddings/exports); backup-purge coordination; per-clinic bounds to police
D63 | 0 | Deployment/Ops | Observability | Lean single-VPS platform observability + alerting | Another stack to run/pay for; alert tuning to avoid noise; separate from clinic-facing error review
D64 | 0 | Compliance | Compliance | GDPR-baseline compliance (Guatemala law + Initiative 6,105) | Local-counsel confirmation still required; consent UX work; ongoing law-change monitoring

## Progress (hidden)
Docmee — Progress Dashboard
Indicative 26-week (6-month) plan · phase %s reflect sealed/in-progress status · charts are live
Phase | Start (wk) | Duration (wk) | End (wk) | Status | % Complete | Done (wk) | Remaining (wk)
0 — Foundation | 0 | 2 | 2 | Sealed | 100 | 2 | 0
1A — Core Bot | 2 | 4 | 6 | Sealed | 100 | 4 | 0
1B — Human Inbox | 6 | 3 | 9 | Sealed | 100 | 3 | 0
1C — Scheduling | 9 | 3 | 12 | Sealed | 100 | 3 | 0
2A — Multi-User Ops | 12 | 2 | 14 | Sealed | 100 | 2 | 0
2B — Channels | 14 | 2 | 16 | Sealed | 100 | 2 | 0
2C — Automation | 16 | 2 | 18 | Sealed | 100 | 2 | 0
2D — Analytics/Search | 18 | 2 | 20 | Sealed | 100 | 2 | 0
3A — Multi-Doctor | 20 | 2 | 22 | Sealed | 100 | 2 | 0
3B — Adv. Intake | 22 | 1 | 23 | Sealed | 100 | 1 | 0
3C — Integrations/OCR | 23 | 2 | 25 | Sealed | 100 | 2 | 0
3D — Mobile/PWA/Push | 25 | 1 | 26 | Sealed | 100 | 1 | 0
Deployment / external actions (from Action Tracker)
Status | Count
Not started | 15
In progress | 2
Closed (done) | 1
Blocked/waiting | 1
Parked | 1
Overall project — phases
Status | Count
Sealed | 12
In progress | 0
Pending | 0
Overall % complete | 100
Requirements delivery schedule (source for Requirements Gantt)
Requirement | Start (wk) | Delivered (wk) | Remaining (wk) | Phase
PR01 IA Studio | 12 | 2 | 0 | 2A
PR02 Clinic Panel | 6 | 3 | 0 | 1B
PR03 Channels | 2 | 4 | 0 | 1A
PR04 Unified Inbox | 6 | 3 | 0 | 1B
PR05 Bot/Human Mode | 2 | 4 | 0 | 1A
PR06 No-Interrupt | 2 | 4 | 0 | 1A
PR07 KB | 2 | 4 | 0 | 1A
PR08 Audio | 2 | 4 | 0 | 1A
PR09 Calendar | 9 | 3 | 0 | 1C
PR10 Data Capture | 6 | 3 | 0 | 1B
PR11 Tags/Status | 6 | 3 | 0 | 1B
PR12 Assignment | 6 | 3 | 0 | 1B
PR13 Notes | 6 | 3 | 0 | 1B
PR14 Reminders | 16 | 1.4 | 0.6 | 2C
PR15 Quick Replies | 12 | 2 | 0 | 2A
PR16 History | 6 | 3 | 0 | 1B
PR17 Metrics | 18 | 0 | 2 | 2D
PR18 Alerts | 6 | 3 | 0 | 1B
PR19 Meta Compliance | 0 | 2 | 0 | 0
PR20 Safety Rules | 2 | 4 | 0 | 1A
PR21 Panel i18n (gap) | 12 | 2 | 0 | 2A
PR22 EN Chatbot (partial) | 18 | 0 | 2 | 2D
PR23 Mobile App | 25 | 0 | 1 | 3D
PR24 Notifications | 12 | 2 | 0 | 2A
PR25 Doc Training | 2 | 4 | 0 | 1A
PR26 Tone Control | 2 | 4 | 0 | 1A
PR27 Clinic Rules | 2 | 4 | 0 | 1A
PR28 Custom Flows | 22 | 0 | 1 | 3B
PR29 Error Review | 18 | 0 | 2 | 2D
PR30 Multi-Doctor | 20 | 0 | 2 | 3A
PR31 Sheets/CRM | 23 | 0 | 2 | 3C
PR32 QoS | 18 | 0 | 2 | 2D

## Security Audit (hidden)
ID | Category | Concern | Details | Blast radius | Priority | Recommended solution | Status
SEC01 | Tenant Isolation | Cross-tenant RLS carve-out leak | A worker/admin code path missing clinic context could read or write across tenants | Catastrophic — all clinics' PHI exposed/crossed | Critical | withClinicContext() everywhere; single named admin role via withAdminContext() (lint-enforced single import) + allowlist + audit (R5) | Mitigated (locked)
SEC02 | Encryption / Keys | Master encryption key compromise | Envelope-encryption master key leak exposes all PHI at rest | Catastrophic — all PHI at rest | Critical | Supabase Vault + envelope + key_version rotation + host-store fallback; restrict key access; rotate on suspicion (X8) | Mitigated (locked)
SEC03 | Encryption / Keys | HMAC lookup-key leak (identity correlation) | Stable HMAC used for encrypted-field lookups; leak enables correlation/brute-force of identities | High — patient identity correlation | High | Separate stable HMAC key, independent of the encryption key; long key; restricted access (R4) | Mitigated (locked)
SEC04 | Third-Party | PHI through unofficial WhatsApp gateway (Evolution) | Interim transport is an unofficial gateway — PHI in transit through a non-official component; ToS + interception risk | High — WhatsApp PHI in transit | High | Bounded interim + supervision; per-clinic cutover to official Meta Cloud API (R7, X9/X10) | Mitigated (interim); cutover planned
SEC05 | Application / Bot | Prompt injection / data exfiltration via patient input | Patient messages may try to manipulate the bot to reveal data or act out of scope | Medium-High — bounded to current clinic/patient by RLS | High | KB-grounded only (no general fallback); RLS-scoped context; DAL allowlist constrains writes; structured system prompt; deterministic gates | Mitigated (by design)
SEC06 | Third-Party | PHI sent to third-party LLM/ASR providers | Messages/audio sent to Anthropic/DeepSeek/OpenAI/Deepgram; data-handling + residency concerns for medical data | High — PHI to external processors | High | Provider data-processing terms + no-train assurances; minimize PHI in prompts; consider self-hosted LLM (FI2) for sensitive deployments | Open — review needed
SEC07 | Auth / Access | RBAC enforced only in UI (privilege escalation) | If the role matrix isn't enforced at API/DAL, a user could call APIs beyond their role | Medium — within-clinic over-access | High | Enforce the 5-role matrix at API/DAL, not UI-only (G18) | Mitigated (locked)
SEC08 | Auth / Access | Platform impersonation abuse | Platform admins can impersonate clinic users; abuse = access to any clinic's PHI | High — any clinic via impersonation | High | acted_by_platform_user_id stamp + audit + time-boxed session + platform-only (G28) | Mitigated (locked)
SEC09 | Network / Transport | Webhook spoofing (unverified inbound) | Unverified Meta webhooks allow forged inbound messages | Medium — injected messages per clinic | High | Meta HMAC signature verification + constant-time compare + verify-challenge (G06) | Mitigated (locked)
SEC10 | Application / Bot | Bot unauthorized data writes | Bot writes to patient records; injection could attempt bad writes | Medium — single patient record | High | DAL allowlist (field-level, validated, logged, NO deletes), confidence-gated, secretary-wins (D24) | Mitigated (locked)
SEC11 | Encryption / Keys | Secrets exposure (env / boot) | Connection secrets in env; leak via misconfig or logs | High — infra credentials | High | env = connection secrets only; master key from Vault at boot; fail-fast; never log secrets (G05) | Mitigated (locked)
SEC12 | Third-Party | OAuth token theft (Google Calendar / Meta) | Stored per-clinic OAuth tokens; theft → calendar/page access | Medium — single clinic's calendar/page | High | Encrypted token storage (envelope); refresh/revocation handling; disconnect alerts (1C/2B) | Mitigated (locked)
SEC13 | Infrastructure | Single-VPS host compromise | All components on one host; host compromise = full compromise; also SPOF | High — entire deployment | Medium-High | Host hardening + least-privilege + patch mgmt; encrypted backups (X12); redundancy later (X13, R8) | Partial — hardening needed
SEC14 | Infrastructure | Backup security (PHI in backups) | DB backups contain PHI; unencrypted/exposed backups = breach | High — all PHI in backup | High | Encrypted backups, access-controlled, tested recovery (X12) | Open — X12 before real patients
SEC15 | Compliance | Messaging opted-out patients | Sending to opted-out users violates policy/regulation | Low-Medium — compliance | Medium | Outbound chokepoint suppression, bot-irreversible (D05) | Mitigated (locked)
SEC16 | Compliance | PHI in logs / URLs | PHI accidentally logged in plaintext or placed in URL query strings | Medium — log/URL exposure | Medium-High | Structured logging that redacts PHI; never put PHI in URLs/query strings; restrict log access | Open — build-time discipline
SEC17 | Auth / Access | JWT / session security | Clinic JWT scope/expiry; stolen-token reuse | Medium — single user/clinic session | Medium-High | Scoped short-lived JWTs; secure storage; rotation; revoke on role change | Locked (scope) + build discipline
SEC18 | Network / Transport | API rate limiting / DoS | Webhook + API endpoints could be flooded or abused | Medium — availability | Medium | Per-source rate limiting; early-drop invalid webhooks; queue backpressure | Open — recommended
SEC19 | Audit / Logging | Audit completeness & tamper-resistance | Admin/impersonation/status changes must be reliably logged for forensics | Low — forensics/accountability | Medium | Append-only, time-stamped, actor-stamped audit logs; immutable storage; access-controlled | Mitigated (locked pattern)
SEC20 | Compliance | Cross-channel merge PHI mixing | A wrong patient merge blends two patients' PHI | Medium — two patients | Medium-High | Manual-only merge, audited, confirmation step (D37); reversible merge → FI6 | Mitigated (manual)
SEC21 | Application / Bot | Distress / safety mishandling | Bot mishandling a medical-distress message (liability/safety, not data) | Low-Medium — reputation/safety | Medium | Deterministic deflection guardrail + local emergency number (D16, R10, X14) | Mitigated (locked)
SEC22 | Infrastructure | Dependency / supply-chain | npm/pip deps + self-hosted Evolution may carry vulnerabilities | Medium — code execution / compromise | Medium | Pinned deps + lockfiles; vuln scanning (npm/pip audit); update cadence; vet Evolution version | Open — recommended
SEC23 | Compliance | Proactive-messaging compliance / WhatsApp number reputation | Improper proactive sends (no opt-out check, spam, marketing without consent) risk policy violation + number throttle/ban | Medium-High — clinic's whole messaging channel | Medium-High | Six-gate model at chokepoint (opt-out, approved-template, timing, state-valid, frequency-cap, clinic-enabled); transactional-only in 2C; marketing deferred w/ explicit opt-in (D39) | Mitigated (six-gate) for transactional
SEC24 | Compliance | External data egress (Sheets/CRM export) | PHI/lead data leaving the platform to a clinic's Sheet or external CRM (3C); risk of over-export or leak to wrong destination | Medium-High — patient data outside platform | Medium-High | Clinic-authorized fields only; per-clinic encrypted OAuth creds (G49); egress audited + revocable (G48); aggregates/scoped where possible | Mitigated (clinic-authorized + audited)
SEC25 | Compliance | Data retention & right-to-erasure | No retention/erasure policy = indefinite PHI accumulation + no deletion path; non-compliant with GDPR-baseline + emerging Guatemalan law | Medium — long-term PHI exposure surface | Medium | Configurable retention + scheduled hard-purge cascade (D62/G62); right-to-erasure via opt-out chokepoint; consent capture (G63); local-counsel review (X20) | Mitigated (D62 retention + G62 cascade)

## Platform Requirements (hidden)
Platform Requirements — spec vs. build cross-check
Source: Docmee_Platform_Requirements_EN.pdf · doc Phase 1→our 0/1A/1B/1C · doc Phase 2→our 2A–2D · doc Phase 3→our 3A–3D
ID | Doc section | Requirement (grouped) | Coverage | Where (our build) | Notes
PR01 | 1. IA Studio Admin Panel | Create/activate clinics, users, roles, chatbot settings, view convos, manage channels, error review, performance, billing, integrations | Planned | 2A (IA Studio+RBAC D33), 2A invoicing (D34), 2D error review | Core admin surface in 2A; billing manual in 2A
PR02 | 2. Clinic Panel | Private per-clinic panel; multi-user roles (doctor/secretary/admin/assistant); role permissions | Covered | 1B (panel/CRM), 2A (RBAC D33) | 5-role matrix locked + enforced at API/DAL
PR03 | 3. Communication Channels | WhatsApp first; then Messenger + Instagram; unified inbox | Covered | 1A (WhatsApp), 2B (Messenger/IG + unified)
PR04 | 4. Unified Inbox | Conversation states, name/phone, channel, history, status, tags, notes, appt status, last interaction | Covered | 1A/1B/2B
PR05 | 5. Bot/Human Mode | Activate/pause/transfer/return bot; detect human-request phrases; mark urgent | Covered | 1A (modes, takeover, intent/handoff, deflection)
PR06 | 6. Bot Must Not Interrupt | Human reply pauses bot; assigned = bot silent; manual/timeout reactivation; show mode | Covered | 1A (takeover-on-reply + self-healing handback) | Core locked principle
PR07 | 7. KB Per Clinic | Own KB; answer only clinic info; rich fields; IA Studio edit; no cross-clinic mixing | Covered | 1A (KB + RLS isolation + grounding)
PR08 | 8. Audio Messages | Transcribe → understand → text reply; audio replies future | Covered | 1A (provider-abstracted transcription)
PR09 | 9. Google Calendar | Availability, schedule, confirm, reschedule, cancel, check existing appt, status query, transfer if not found | Partial | 1C (schedule/availability), 2C (confirm), gap-closure (bot status-query) | Closed by decision: bot now answers appt-status query (reads Calendar, not-found→human); reschedule/cancel DELIBERATELY human-routed for safety (bot-driven → FI7)
PR10 | 10. Patient Data Capture | Name, phone, reason, preferred date/time, doctor/specialty, new/returning, channel, notes | Covered | 1B (capture D24) + 1C (intake); doctor/specialty → 3A
PR11 | 11. Tags & Statuses | Suggested tags + conversation statuses | Covered | 1B (tags + patient status; conversation status = mode) | Mode (bot/human/paused/resolved) maps to the doc's statuses; no duplicate status system
PR12 | 12. Conversation Assignment | Assign to secretaries / doctor / admin | Covered | 1B (assignment) + 2A (routing D30)
PR13 | 13. Internal Notes | Staff-only notes inside conversations | Covered | 1B (patient/conversation notes D22)
PR14 | 14. Follow-Ups & Reminders | 1-day reminder, confirmation, post-consult, 7-day, 3-month, review, no-reply; template-gated | Covered | 2C (reminders/confirmations/follow-ups, six-gate, templates)
PR15 | 15. Quick Reply Templates | Canned responses (address/hours/price/etc.) | Covered | 2A (quick replies D32)
PR16 | 16. Patient History | Prev convos/appointments, status, notes, tags, last interaction, next appt; not a medical record | Covered | 1B (profile) + 1C (appointments)
PR17 | 17. Basic Metrics | Totals, by channel, leads, requests, scheduled, transfers, common Qs, peak hours, no-response, conversion | Planned | 2D (Analytics)
PR18 | 18. Secretary Alerts | Human-request, bot-stuck, appt request, urgent, upset, needs confirmation, repeated no-response | Covered | 1B (notifications) + 2A (full escalation D31)
PR19 | 19. Meta Compliance & Account Protection | API use, verification, webhooks, token storage/renewal, windows, approved templates, no mass-msg w/o consent, consent, opt-out, anti-spam, quality monitoring, Meta error logs | Covered | P0 (webhook/tokens/opt-out), 1A (window), 2C (templates/six-gate/consent), 2D (quality/error logs), X1/X3/X4 | 'No mass messaging w/o consent' = 2C Q5 broadcast flag
PR20 | 20. Medical Safety Rules | No diagnose/prescribe/treat/interpret/replace; suggest appointment; emergency → emergency services | Covered | 1A (deflection guardrail + behavioral rules D16)
PR21 | 21. Spanish & English PANEL | Panel i18n; language switch; applies to all admin/clinic UI | Planned | Gap-closure (i18n framework from start) across panel | LOCKED — ES+EN panel i18n: keys + per-user locale switch across IA Studio + clinic panel; panel language independent of chatbot
PR22 | 22. Spanish & English CHATBOT | Bot understands + replies in patient language (Spanish + English) | Planned | Gap-closure (amends 1A): detect + respond in patient language | LOCKED — ES+EN chatbot: detect patient language, reply in it using clinic-approved info; further languages → FI
PR23 | 23. Mobile App Vision | Eventual app (UChat-like); responsive → PWA → native | Planned | 3D (PWA + Web Push) + FI4 (native app) | Locked in 3D — responsive panel + installable PWA + push; native iOS/Android remains FI4
PR24 | 24. Notifications | Triggers; web panel / email / mobile-PWA / internal-WhatsApp (future) | Covered | 1B + 2A (panel/email) + 3D (Web Push); internal-WhatsApp = future | Push channel locked in 3D (VAPID) into the notification ladder
PR25 | 25. Document Training | PDF/Word/text/FAQ ingestion into the KB | Covered | 1A (text-layer) + 3C (OCR + docx/structured parsers) | Basic text ingestion in 1A; OCR for scanned docs + rich formats locked in 3C
PR26 | 26. Bot Tone Control | Formal / friendly / professional / short / detailed / secretary-style | Planned | 3B (tone = per-clinic rule setting) + 1A | Locked in 3B advanced rules — tone becomes a structured per-clinic rule
PR27 | 27. Clinic-Specific Rules | No prices / only consult price / no medical Q / transfer emergencies / no booking w/o payment / after-hours data-only / transfer certain cases | Planned | 3B (structured conditional rules) + 1A (D10/D16) | Locked in 3B — safety-critical rules (payment-gate, after-hours) enforced deterministically at pipeline gates
PR28 | 28. Custom Flows | Schedule/reschedule/confirm/location/price/surgery/post-consult/review/insurance | Planned | 3B (declarative flow builder) + 1C/2C/1A | Locked in 3B — clinic-configurable flow builder + starter library; individual flows already exist
PR29 | 29. Error Review Area | Unanswered, help requests, bad responses, handoffs, unknown intents, Meta/Calendar errors, failed messages | Planned | 2D (error review) | Infra exists: error_log/DLQ
PR30 | 30. Multi-Doctor Clinics | Multiple doctors; per-doctor calendar/services/hours/FAQs; scheduling by doctor | Planned | 3A (Multi-Doctor) | Seam reserved since Phase 0 (dormant doctor tables)
PR31 | 31. Sheets / CRM Integration | Export patient/lead fields to Sheets or external CRM | Planned | 3C (Sheets append + generic webhook/CRM connector) | Locked in 3C — per-clinic export, encrypted creds (X18), clinic-authorized fields only (SEC24)
PR32 | 32. QoS Monitoring | Upset patients, abandoned, response times, no closure, no-schedule reasons, follow-up opportunities | Planned | 2D (QoS/analytics)

## Cost Tracker (hidden)
Docmee — Cost Tracker
Deliverables vs. time spent and AI-assistant cost. Blue input cells are editable; costs are live formulas. Fill Actual hrs + AI uses as you go.
Assumptions (edit these)
Parameter | Value
Dev rate ($/hr) | 20
AI cost per use ($/session) | 0.5
Hours per week (capacity) | 25
Cost tracker (by deliverable)
ID | Deliverable | Weeks | Est. hrs | Actual hrs | Dev cost | AI uses | AI cost | Total cost | Notes
P0 | 0 — Foundation | 2 | 50 |  | 0 |  | 0 | 0
P1A | 1A — Core Bot | 4 | 100 |  | 0 |  | 0 | 0
P1B | 1B — Human Inbox | 3 | 75 |  | 0 |  | 0 | 0
P1C | 1C — Scheduling | 3 | 75 |  | 0 |  | 0 | 0
P2A | 2A — Multi-User Ops | 2 | 50 |  | 0 |  | 0 | 0
P2B | 2B — Channels | 2 | 50 |  | 0 |  | 0 | 0
P2C | 2C — Automation | 2 | 50 | 1.5 | 30 | 6 | 3 | 33 | 2C Q1–Q4 decision work (this session) — estimate
P2D | 2D — Analytics/Search | 2 | 50 |  | 0 |  | 0 | 0
P3A | 3A — Multi-Doctor | 2 | 50 |  | 0 |  | 0 | 0
P3B | 3B — Adv. Intake | 1 | 25 |  | 0 |  | 0 | 0
P3C | 3C — Integrations/OCR | 2 | 50 |  | 0 |  | 0 | 0
P3D | 3D — Mobile/PWA/Push | 1 | 25 |  | 0 |  | 0 | 0
PM | PM — Planning, decisions & tracker (cross-cutting) | 0 | 0 | 3.5 | 70 | 18 | 9 | 79 | This session: tracker build, dark mode, Gantts, Platform Requirements, Cost Tracker, Overview fixes — estimate
| TOTAL | 26 | 650 | 5 | 100 | 24 | 12 | 112
Summary
Total dev cost | 100
Total AI cost | 12
Grand total | 112
Est. hrs (plan) | 650
Actual hrs (logged) | 5
AI uses (logged) | 24

## Build Backlog (hidden)
Docmee — Build Backlog (sequenced from sealed plan)
Build top-to-bottom. Gates = definition of done · Gaps = impl rules · Actions/Security = pre-conditions. Companion: docmee-build-backlog.md
Order | Stage | Build focus | Gates | Gaps | Actions (pre-cond) | Security | Notes
S0 | Sprint 0 | Setup + unblock externals + SEC06 decision | — | — | X7·X20·X1·X5·X6·X2·X9 | SEC06·SEC22 | Start Meta + counsel NOW (lead time); stand up infra + CI + observability (D63)
1 | Phase 0 — Foundation | RLS isolation · encryption · opt-out chokepoint · idempotency · deploy | 9 | G01–G08·G62·G63 | X6 | SEC16 | Build the RLS tenant-isolation test suite here
2 | Phase 1A — Core Bot | KB · 5-intent pipeline · 24h window · transcription · ES/EN bot | 10 | G09–G13 | X5 | SEC06 | Grounded answers; never interrupts a human
3 | Phase 1B — Human Inbox | Patient CRM · assignment · tags · notes · capture allowlist | 16 | G14–G18 | — | — | Secretaries fully operate inbox
4 | Phase 1C — Scheduling | Calendar truth · 8-step intake · lifecycle · status query | 14 | G19–G25 | X15 | — | Reschedule/cancel route to humans
★ | PILOT LAUNCH GATE | Pre-conditions before ANY real patient traffic | — | — | X3·X7·X12·X14·X11·X20 | SEC14·SEC18 | All must pass before go-live
5 | Phase 2A — Multi-User Ops | RBAC · IA Studio · routing · notifications · panel i18n | 11 | G26–G28 | — | — | ES/EN panel i18n here
6 | Phase 2B — Channels | Messenger + IG · unified inbox · manual merge | 8 | G29–G31 | X16 | — | Manual merge only (FI6 later)
7 | Phase 2C — Automation | Templates · six-gate · reminders · follow-ups | 4 | G57–G61 | X4 | SEC23 | Build six-gate + idempotency test suite here
8 | Phase 2D — Analytics & Search | Metrics/QoS rollups · error review · content search | 3 | G32–G36 | — | SEC16 | Resolves R12
9 | Phase 3A — Multi-Doctor | Doctor entity · selection · per-doctor KB/routing | 4 | G37–G41 | X17 | — | N=1 backward compatible
10 | Phase 3B — Advanced Intake | Flow builder · advanced rules · secretary copilot | 3 | G42–G46 | — | — | Safety rules enforced deterministically
11 | Phase 3C — Integrations & OCR | OCR ingestion · Sheets/CRM export · reports | 3 | G47–G51 | X18 | SEC24 | Export requires written consent (Guatemala law)
12 | Phase 3D — Mobile/PWA/Push | Installable PWA · Web Push · mobile parity | 3 | G52–G56 | — | — | Native app = FI4
~ | Ongoing / parked | Testing (X19) · observability (D63) · HA (X13 parked) | — | — | X19·X11·X13 | SEC06·14·16·18·22 | Pull RLS+six-gate tests into the build